Workload Discovery and Migration Planning Playbook

- Verify all server information has been collected. This should be a detailed list that includes at least the information in the migration worksheet server list.

- Plan discovery depending on the complexity of the workload:

  - Option 1 – Complex Workloads. Send the workload discovery template to the application owners to fill out and send back. This will allow for time to review internally and itemize any concerns, discussion points, and follow up before a meeting. When review is complete, schedule a meeting (generally 1-2 hours) with the designated workload owners and infrastructure/network/DB resources to review in detail.

  - Option 2 – Less Complex Workloads or single servers. Schedule a meeting (generally 1-2 hours) with the designated workload owners and infrastructure/network/DB resources. Fill out required parts of the workload discovery template together over a screenshare and discuss all dependencies and prerequisites activities. Make sure to inventory all items in the necessary sections to develop a migration plan.

- Document all data in the migration worksheet and create a migration plan. The migration plan should be detailed – it should include tasks for all parties involved as well as a time estimate for each task or group of tasks. Each task or group of tasks should have a clearly defined owner or owners.

- Schedule a migration plan review session (1 hour) with the application owners, business owners, and infrastructure/network/DB resources. Review the migration plan in detail and adjust as needed. Discuss planning the cutover window and duration. If the window has already been established, get a decision on whether to proceed or reschedule.

- Work with the client to schedule the cutover window. For any production or impacting workloads, the window should include a conference call and ideally a Teams meeting (or similar) for screensharing and chat.

  - When planning the window duration make sure to account for testing time as well as testing time + rollback if necessary. The time should be estimated cutover time + testing time + estimated rollback time. For example, 1 hour to cutover + 2 hours testing + 1 hour to rollback = 4 hour window.