## Migration Group Overview
Migration Worksheet
Workload and Resource Information
Information about the workload being migrated and contact information.
Client | pepsico
App/Workload Group Name(s) | Hanson Financials
| Resource Name(s) | Contact Information | Resource Name(s) | Contact Information
Client Project Lead
App Owner(s)
Dev/App Support Resource
Systems Team Resource
Network Team Resource
DBA Team Resource
Ops Team Resource
MBG Resources
Key Migration Dates
Migration dates to track - communication dates, prerequisite completion, cutover window, etc
| Date | Status
Communication 1
Communication 2
Communication 3
Prerequisite Completion
Prerequisite Validation
Planning Meetings
Cutover Window
Cutover Window Duration
Migration Strategy
Very high level overview of how the migration will be performed. Update as needed per app/workload group. - ASR will be utilized to replicate the servers to Azure - Any prerequisite build/config activites will be performed and verified before the scheduled cutover by the client IT team and MBG - Any cutover specific prerequisite activities will be performed at the beginning of the window, for example DNS changes. If any special process or steps need to be followed before migration, list them here and account for them in the checklist. - ASR failover will take take place after any prerequisite activites has been verifed as completed. If any special process or steps need to be followed during or after migration, list them here and account for them in the checklist. - MBG and client IT teams will verify the servers are available with network connectivity - If any reconfiguration of the servers or application are required, they will be completed by the client IT team after failover - If any post configuration activities are to be performed, list them in the cutover checklist and make sure any supporting information is in the Server List (Log Analytics, RSV, etc) - Any application or server testing will take place by the client IT team after failover - Stakeholders will sign off that the migration group is functioning as expected and has been completed. MBG will stop replication and remove the item from the SIte Recovery configuration.
Migration Checklist
Rollback Checklist
In Scope Server List
Issues and Actions Log

## Tagging
Workload Tagging List These tags will be added to all workload resources post-migration. These are just examples, modify as needed for the client and workload.
Tag Name | Value
Workload | ExampleApp
Environment | Production
SupportContact | support@email.com
CreatedBy | 10th Magnitude
ManagedBy | 10th Magnitude
CostCenter | 123456
Department | Finance

## Pre-Cutover Checklist
Pre-Failover Configuration Checklist - Modify as Needed |  |  | Status Tracker
Task # | Task Detail | Team | SampleApp1 | SampleApp2
1 | Provide ASR service account with local administrative rights on the server(s) in scope for migration to push the ASR Mobility Agent and connect to perform post-migration setup. | Client | Incomplete | Incomplete
2 | Enable EMS on all migrating Windows servers | Client | Incomplete | Incomplete
3 | If VMware VMs, verify the NIC is VMXnet3 (E1000 NICs are not recommended). | Client | Incomplete | Incomplete
4 | Remove from SCCM/WSUS management | Client | Incomplete | Incomplete
5 | Determine if any parts of the workload will be load balanced. Existing or create new? Provide information if CMC will need to create a load balancer or app gateway. | 10M Project Leadership | Incomplete | Incomplete
6 | Determine if the application is tiered and which tier each server belongs to. | 10M Project Leadership | Incomplete | Incomplete
7 | Determine if any special hardware configurations. | 10M Project Leadership | Incomplete | Incomplete
8 | Determine if availability sets will be used for any of the machines and if the CMC needs to create them. | 10M Project Leadership | Incomplete | Incomplete
9 | Provide a list of tags and values for each workload. | 10M Project Leadership | Incomplete | Incomplete
10 | Fill in all columns of the migration group worksheet. | 10M Project Leadership / CMC | Incomplete | Incomplete
11 | Create and configure load balancer or app gateway. | CMC | Incomplete | Incomplete
12 | Create availability sets. | CMC | Incomplete | Incomplete
13 | Create any additional required resources prior to migration. |  | Incomplete | Incomplete

## Sample Cutover Checklist
Sample Workload Migration / Cutover Checklist
Task # | Task / Subtask Detail | Team | Task Lead /Contact Info | Task Notes & Comments | Est. Duration | Est. Start | Est. End | Actual Start | Actual End | Results / Notes for Post-Change Triage
1 | Migration group team member kickoff / planning call | MBG
2 | Verify prerequisites are completed | MBG/Client
2.1 | Take backups of on-prem machines | Client DB Team
2.2 | VNETs created and DNS configured to point at new Azure DCs | Client Network Team
2.3 | NSGs created and applied | Client Network Team
2.4 | Network landing information documented per server in the spreadsheet | Client Network Team
2.5 | Firewall rules in place and tested if possible | Client Network Team
2.6 | App Gateways or front end LB built and configured - Backend pools / listeners / rules | Client Network Team
2.7 | Certificates installed on front end | Client Team
2.8 | Landing Resource Groups created and documented per workload/server | MBG
2.9 | Landing Availability Groups created and documented per workload/server
2.10 | Service endpoints configured if required | MBG
2.11 | ASR Target server configurations verified | MBG
2.12 | Assign static IPs to target servers configurations, if applicable | MBG
2.13 | Failover testing has been completed | Client Team/MBG
2.14 | Failover and post failover plans created in Azure and reviewed | MBG
2.15 | Seek Change Request approval and define cutover window | Client Team
2.16 | Schedule App/DBA team support for the cutover activities | Client Team |  |  |  | At least 3 days prior
2.17 | Send first communication | Client Team |  |  |  | 1-2 weeks prior
2.18 | Send second communication | Client Team |  |  |  | 2 days -1 week prior
2.19 | Bypass/modify policy for failed over machines | Client Team
3 | Send final communication | Client Team |  |  |  | Day of window
4 | Validate replication and proper RPO target is being met | MBG
Cutover Window Start
5 | Start migration meeting | MBG/Client
5.1 | Verify necessary parties are present needed to proceed | MBG/Client
5.2 | Send notification if necessary | Client Team
6 | Verify prerequisites are completed | MBG/Client
6.1 | Verify backups are complete, if applicable | Client Infrastructure Team
7 | Execute ASR failover | MBG
8 | Validate on-prem servers are shut down | Client Infrastructure Team
9 | Conduct functional server validation tests | MBG/Client
9.1 | Verify clean boot | MBG/Client
9.2 | Verify network connectivity | MBG/Client
9.3 | Verify name resolution | MBG/Client
10 | Individual Server Validation | Client Infrastructure Team
10.1 | Test RDP/SSH to servers | Client Infrastructure Team
10.2 | Validate Server Ceritificate, if Applicable | Client Infrastructure Team
10.3 | Network Connectivity Test to other migrated resources, DB etc | Client Infrastructure Team
10.4 | Verify File Shares
11 | Update / Validate App Gateway / LB Certificate | Client Network Team
12 | Update / Validate AG or Load Balancer Pools and Check Health | Client Network Team
13 | Update / Validate DNS Changes | Client Infrastructure Team
14 | App Config Changes & Validation | Client Infrastructure Team
14.1 | Update DB Connection String in Config File | Client Infrastructure Team
14.2 | App Services Start/Restart
14.3 | Validate IIS Settings | Client Infrastructure Team
15 | Conduct functional application validation tests | Client Application Team
15.1 | Application Functionality Test in IIS | Client Infrastructure Team
15.2 | Application Load Test | Client Infrastructure Team
16 | Receive final confirmation from all testers | MBG/Client
Proceed / Rollback Decision
17 | Windows VMs - Enable serial console bcdedit /ems '{current}' ON bcdedit /emssettings EMSPORT:1 EMSBAUDRATE:115200 | Client Infrastructure Team
18 | Windows VMs - Verify the temporary drive is online in the OS | Client Infrastructure Team
19 | Windows VMs - Move the PageFile to the temporary drive Set-ItemProperty -Path 'HKLM:\SYSTEM\CurrentControlSet\Control\Session Manager\Memory Management' -name "PagingFiles" -Value "D:\pagefile.sys" -Type MultiString -force | Client Infrastructure Team
20 | Setup Operations | MBG
20.1 | Install MMA and any needed additional extensions on migrated servers | MBG
20.2 | Enable Monitoring | MBG
20.3 | Enable Backups | MBG
20.4 | Verify the servers are members of a patching schedule | MBG
21 | Reboot the VM to apply up the serial and pagefile changes | Client Infrastructure Team
22 | Add proper tags to the VMs | MBG |  |  | 0:05
23 | Update Monitoring | Client Team |  |  | 0:10
24 | Send out completion notice | Client Team |  |  | 0:05
25 | Uninstall Mobility service from Azure servers if necessary | Client Team |  |  | 0:30
Cutover Window End
26 | Post migration Application benchmark testing (if applicable) | Client Application Team
27 | Follow up with app and business owners | MBG/Client
28 | Debrief and capture lessons learned | MBG

## Post-Cutover Checklist
Post-Failover Configuration Checklist - Modify as Needed |  |  | Status Tracker
Task # | Task Detail | Team | SampleApp1 | SampleApp2
1 | Connect to Log Analytics Workspace | 10M CMC | Incomplete | Incomplete
2 | Install the Microsoft Monitoring Agent extension (verify installed automatically when connected to the workspace) | 10M CMC | Incomplete | Incomplete
3 | Enable Azure backups | 10M CMC | Incomplete | Incomplete
4 | Reconfigure boot diagnostics to use shared storage account | 10M CMC | Incomplete | Incomplete
5 | Add requested tags to all workload related resources | 10M CMC | Incomplete | Incomplete
6 | If handing off to 10M Managed Services, send email to msp-tams@10thmagnitude.com with all information for onboarding. | 10M CMC | Incomplete | Incomplete
7 | Move objects to Azure OU in Active Directory if applicable | Client | Incomplete | Incomplete
8 | Stops backups on-prem | Client | Incomplete | Incomplete
9 | Disconnect virtual network adapter and Label servers as migrated so lthey are not accidentally powered back on in the on-prem environment. | Client | Incomplete | Incomplete
10 | Verify VMs are added to a patching schedule | Client / 10MS | Incomplete | Incomplete

## Rollback Checklist
Rollback Checklist
Task # | Status | App | Task / Milestone / Phone Call | Team | Primary Resp. / Phone | Critical Path | Task Notes & Comments | Est. Duration | Est. Start | Est. End | Actual Start | Actual End | Results / Notes for Post-Change Triage
1 |  |  | Shut down migrated Azure servers | 10M
2 |  |  | Boot on-prem servers | Client Infrastructure Team
3 |  |  | Update / Validate Internal/External DNS records | Client Infrastructure Team
4 |  |  | Conduct functional server validation tests | Client Infrastructure Team
5 |  |  | Verify clean boot | Client Infrastructure Team
6 |  |  | Verify network connectivity | Client Infrastructure Team
7 |  |  | Verify name resolution | Client Infrastructure Team
8 |  |  | Conduct functional application validation tests | Client Application Team
9 |  |  | Receive final confirmation from all testers | 10M/Client
10 |  |  | Schedule review meeting to discuss reason for backout and next steps | 10M/Client