## Sheet1
2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32
Pilot
| Archeology | Review/Replicate | Non-Prod | Production | Support
Migration Group 1
|  |  | Archeology | Review/Replicate | Non-Prod | Production | Support | Support
Migration Group 2
[5 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 3
[8 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 4
[7 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 5
[8 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 6
[9 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 7
[10 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 8
[11 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 9
[12 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 10
[13 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 11
[14 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 12
[15 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 13
[16 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 14
[17 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 15
[18 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 16
[19 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 17
[20 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 18
[21 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 19
[22 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 20
[23 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 21
[24 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 22
[25 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 23
[26 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
We are here.

## Sheet3
"Small Migration Plan" |  |  | Phase 1
Server Count under 200 |  |  | Kick-Off, Planning, Setup, & Discovery |  |  | Phase 2
Migration
Phase 3
Phase 3 - Support & Cleanup
|  |  | Month 1 |  |  |  | Month 2
| Week | Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[15 empty] | Hours | Rate | Total | Server Count | Cost / Server
Program Leadership | Delivery Director | [13 empty] | 0 | 235 | 0 | 60 | 0
| Architect | [13 empty] | 0 | 300 | 0 | 75 | 0 | bar: Month 1 1 to Month 2 9
CBA | bar: Month 1 4 to Month 2 9
| TOM | [13 empty] | 0 | 195 | 0 | 100 | 0
| Mig. Engineer | [13 empty] | 0 | 145 | 0 | 150 | 0
0
| Move Groups |  | Month 1 4: Migration Group 1
[6 empty] | Discovery | Non-prod | Production | Support
Migration Group 2
[8 empty] | Discovery | Non-prod | Production | Support
| Servers Migrated | [13 empty] | 20-60 | Total | bar: Month 2 5 to Month 2 6
[15 empty] | 40-100 | 60-160 | bar: Month 2 7 to Month 2 8
Team Model
[9 empty] | 3 month | 500+
6 month
12 month

## Sheet3 (2)
"Super Small Migration Plan" |  | Phase 1
Server Count under 50 |  | Kick-Off, Planning, Setup, & Discovery |  |  | Phase 2
Migration
Phase 3
Phase 3 - Support & Cleanup
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
[13 empty] | Hours | Rate | Total | Server Count | Cost / Server
| Delivery Director | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  | 160 | 235 | 37600 | 60 | 1013.3333
| Architect | [11 empty] | 0 | 300 | 0 | 75 | 810.6667 | bar: 1 to Phase 3 - Support & Cleanup 9
| Mig. Analyst | [11 empty] | 0 | 195 | 0 | 100 | 608 | bar: 1 to 5
| Mig. Engineer | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  | 160 | 145 | 23200 | 150 | 405.3333
60800
| Move Groups | 4: Migration Group 1 |  |  |  | 20 | 3040
|  | 4: Discovery; 5: Non-prod; 6: Production; 7: Support |  |  |  | 50 | 1216
[16 empty] | 20 | 10000
| Servers Migrated | 5: 10-30; 6: 10-30 | 20-60 | Total
|  | 7: 20-50; 8: 20-50 | 40-100 | 60-160
|  |  |  | Enterprise | SMB
|  |  |  | 3mo | up to 50
|  |  |  | 6mo | 50-200
12mo

## Sheet2
|  | Tues Thurs | Saturday
Pilot
Archeology | Review/Replicate | Non-Prod | Production | Support
asdfasdflkj | ;lkj;klj
asdfasdflkj | ;lkj;lkj | 1 | 1
asdfasdflkj | ;lkj;lkj
asdfasdflkj
|  | 54 | 54