## Workload List
Workload Group | Workload Name | Status | Business Criticality | Risk Level | Planned Start Date | Owner Name | Owner Contact Info | Other technical contacts | Other business contacts | Third-party support contacts | Migration Method
1 | WorkplaceApp | Complete | Low | Low | 2020-06-12 | Bill Jackson | bjackson@email.com | John Doe (jdoe@email.com) | Ann Frank (afrank@email.com) | N/A | ASR
1 | MarketingWeb | Migration | Medium | Low | 2020-06-13 | Bill Jackson | bjackson@email.com | John Doe (jdoe@email.com) | Ann Frank (afrank@email.com) | N/A | ASR
2 | BI | Discovery | Medium | High | 2020-06-22 | Bill Jackson | bjackson@email.com | John Doe (jdoe@email.com) | Ann Frank (afrank@email.com) | N/A | ASR
2 | TimeKeeper | Discovery | High | Low | 2020-06-22 | Bill Jackson | bjackson@email.com | John Doe (jdoe@email.com) | Ann Frank (afrank@email.com) | N/A | ASR

## Server List
On-Prem Server Info | [12 empty] | Azure Landing Info
Workload Name | Current Server Name | Status | Current Location | Environment | Current Server IP Address | Server OS and Version | Server Description | Replication Start Date and Time | Planned Cutover Date | Planned Cutover Time | Third Party Support | Notes and/or Risks | New Azure Name (if changing) | Landing Subscription | Landing Region | Landing Resource Group | Landing Network | Landing Subnet | Landing IP | Availability Set Name | Load Balancer or App Gateway Name | Migration Method | Recommended VM Series | Recommended Disk Performance | Log Analytics Workspace | Diagnostics Logs Storage Account | Recovery Services Vault (Backups)
WorkplaceApp | Server01 | Ready for cutover | DC01 | Prod | 10.0.0.1 | Windows 2012 R2 | App front end | 11/20/2019 Anytime | 2020-12-01 | 9:00AM CST | N/A |  | Server01 | Prod-Apps01 | Central US | CUS-PRD-Workplace | ProdVNET01 | ProdSubnet01 | DHCP | AVSet01 | CUS-PRD-LB01 | ASR | D2s | Standard SSD for OS Premium SSD for Data | CUS-SHRD-LA | sharediagsto01 | CUS-SHRD-RSV
WorkplaceApp | Server02 | Ready for cutover | DC01 | Prod | 10.0.0.2 | Windows 2012 R2 | App front end | 11/20/2019 Anytime | 2020-12-01 | 9:00AM CST | N/A |  | Server02 | Prod-Apps01 | Central US | CUS-PRD-Workplace | ProdVNET01 | ProdSubnet01 | DHCP | AVSet01 | CUS-PRD-LB01 | ASR | D2s | Standard SSD for OS Premium SSD for Data | CUS-SHRD-LA | sharediagsto01 | CUS-SHRD-RSV
WorkplaceApp | Server03 | Ready for cutover | DC01 | Prod | 10.0.0.3 | Windows 2012 R2 | Processing server | 11/20/2019 Anytime | 2020-12-01 | 9:00AM CST | N/A |  | Server03 | Prod-Apps01 | Central US | CUS-PRD-Workplace | ProdVNET01 | ProdSubnet01 | DHCP | N/A | N/A | ASR | D2s | Standard SSD for OS Premium SSD for Data | CUS-SHRD-LA | sharediagsto01 | CUS-SHRD-RSV
WorkplaceApp | Server04 | Ready for cutover | DC01 | Prod | 10.0.0.4 | Windows 2012 R2 | Queue Server | 11/20/2019 Anytime | 2020-12-01 | 9:00AM CST | N/A |  | Server04 | Prod-Apps01 | Central US | CUS-PRD-Workplace | ProdVNET01 | ProdSubnet01 | DHCP | N/A | N/A | ASR | D2s | Standard SSD for OS Premium SSD for Data | CUS-SHRD-LA | sharediagsto01 | CUS-SHRD-RSV
WorkplaceApp | Server05 | Ready for cutover | DC01 | Prod | 10.0.0.5 | Windows 2012 R2 | DB Server | 11/20/2019 Anytime | 2020-12-01 | 9:00AM CST | N/A |  | Server05 | Prod-Apps01 | Central US | CUS-PRD-Workplace | ProdVNET01 | ProdSubnet01 | DHCP | N/A | N/A | ASR | D2s | Standard SSD for OS Premium SSD for Data | CUS-SHRD-LA | sharediagsto01 | CUS-SHRD-RSV