## Migration Group Overview
Migration Worksheet
Workload and Resource Information
Information about the workload being migrated and contact information.
Client
App/Workload Group Name(s)
| Resource Name(s) | Contact Information | Resource Name(s) | Contact Information
Client Project Lead
App Owner(s)
Dev/App Support Resource
Systems Team Resource
Network Team Resource
DBA Team Resource
Ops Team Resource
Migration Team Resources
Key Migration Dates
Migration dates to track - communication dates, prerequisite completion, cutover window, etc
| Date | Status
Communication 1
Communication 2
Communication 3
Prerequisite Completion
Prerequisite Validation
Planning Meetings
Cutover Window
Cutover Window Duration
Migration Checklist
Rollback Checklist
In Scope Server List
Issues and Actions Log

## Server List
Workload Name | Current Server Name | Current Server IP Address | Environment | Server Description | Replication Start Date and Time | Planned Cutover Date | Planned Cutover Time | Status | Current Location | New Azure Name (if changing) | Server OS and Version | Landing Subscription | Landing Region | Landing Resource Group | Landing Network | Landing Subnet | Landing IP | Azure Tags to Apply | Availability Set Name | Load Balancer or App Gateway Name | Migration Method | Recommended VM Series | Recommended Disk Performance | Log Analytics Workspace | Diagnostics Logs Storage Account | Recovery Services Vault (Backups) | Third Party Support | Notes and/or Risks
EXAMPLE | Server01 | 10.0.0.1 | Prod | Marketing web app server. | 11/20/2019 Anytime | 2020-12-01 | 9:00AM CST | Replicated | DC01 | N/A | Windows 2012 R2 | Prod-Sub01 | East US 2 | EUS2Prod01 | ProdVNET01 | ProdSubnet01 | 10.88.0.5 | Owner: Joe CostCenter: IT | AVSet01 | N/A | ASR | 10vu Recommendation | 10vu Recommendation | shared-ws01 | sharediagsto01 | backup-rsv01 | Vendor Name | Need to work with WebSoft vendor support to verify app functionality after failover.
EXAMPLE | Server02 | 10.0.0.2 | Test | Mail app server. | 11/20/2019 9:00PM | 2020-12-01 | 9:00AM CST | Replicated | DC01 | AZServer02 | Red Hat 7.5 | Prod-Sub02 | Central US | CUSProd01 | ProdVNET02 | ProdSubnet02 | DHCP | Owner: Bill CostCenter: Finance | AVSet02 | lb01 | Build New | D2s | Standard SSD for OS Premium SSD for Data | shared-ws01 | sharediagsto01 | backup-rsv01 | N/A

## Pre-Failover Checklist
Pre-Failover Configuration Checklist - Modify as Needed |  |  | Status Tracker
Task # | Task Detail | Team | SampleApp1 | SampleApp2
1 | Provide ASR service account with local administrative rights on the server(s) in scope for migration to push the ASR Mobility Agent and connect to perform post-migration setup. | Client | Incomplete | Incomplete
2 | Enable EMS on all migrating Windows servers | Client | Incomplete | Incomplete
3 | If VMware VMs, verify the NIC is VMXnet3 (E1000 NICs are not recommended). | Client | Incomplete | Incomplete
4 | Remove from SCCM/WSUS management | Client | Incomplete | Incomplete
5 | Determine if any parts of the workload will be load balanced. Existing or create new? Provide information if Migration Team will need to create a load balancer or app gateway. | Migration Team Project Leadership | Incomplete | Incomplete
6 | Determine if the application is tiered and which tier each server belongs to. | Migration Team Project Leadership | Incomplete | Incomplete
7 | Determine if any special hardware configurations. | Migration Team Project Leadership | Incomplete | Incomplete
8 | Determine if availability sets will be used for any of the machines and if the Migration Team needs to create them. | Migration Team Project Leadership | Incomplete | Incomplete
9 | Provide a list of tags and values for each workload. | Migration Team Project Leadership | Incomplete | Incomplete
10 | Fill in all columns of the migration group worksheet. | Migration Team Project Leadership / Migration Team | Incomplete | Incomplete
11 | Create and configure load balancer or app gateway. | Migration Team | Incomplete | Incomplete
12 | Create availability sets. | Migration Team | Incomplete | Incomplete
13 | Create any additional required resources prior to migration. |  | Incomplete | Incomplete

## Post-Failover Checklist
Post-Failover Configuration Checklist - Modify as Needed |  |  | Status Tracker
Task # | Task Detail | Team | SampleApp1 | SampleApp2
1 | Connect to Log Analytics Workspace | Migration Team | Incomplete | Incomplete
2 | Install the Microsoft Monitoring Agent extension (verify installed automatically when connected to the workspace) | Migration Team | Incomplete | Incomplete
3 | Enable Azure backups | Migration Team | Incomplete | Incomplete
4 | Reconfigure boot diagnostics to use shared storage account | Migration Team | Incomplete | Incomplete
5 | Add requested tags to all workload related resources | Migration Team | Incomplete | Incomplete
6 | If handing off to Managed Services, send email to msp-tams@10thmagnitude.com with all information for onboarding. | Migration Team | Incomplete | Incomplete
7 | Move objects to Azure OU in Active Directory if applicable | Client | Incomplete | Incomplete
8 | Stops backups on-prem | Client | Incomplete | Incomplete
9 | Disconnect virtual network adapter and Label servers as migrated so lthey are not accidentally powered back on in the on-prem environment. | Client | Incomplete | Incomplete
10 | Verify VMs are added to a patching schedule | Client / Migration TeamS | Incomplete | Incomplete

## Rollback Checklist
Rollback Checklist
Task # | Status | App | Task / Milestone / Phone Call | Team | Primary Resp. / Phone | Critical Path | Task Notes & Comments | Est. Duration | Est. Start | Est. End | Actual Start | Actual End | Results / Notes for Post-Change Triage
1 |  |  | Shut down migrated Azure servers | Migration Team
2 |  |  | Boot on-prem servers | Client Infrastructure Team
3 |  |  | Update / Validate Internal/External DNS records | Client Infrastructure Team
4 |  |  | Conduct functional server validation tests | Client Infrastructure Team
5 |  |  | Verify clean boot | Client Infrastructure Team
6 |  |  | Verify network connectivity | Client Infrastructure Team
7 |  |  | Verify name resolution | Client Infrastructure Team
8 |  |  | Conduct functional application validation tests | Client Application Team
9 |  |  | Receive final confirmation from all testers | Migration Team/Client
10 |  |  | Schedule review meeting to discuss reason for backout and next steps | Migration Team/Client

## Sample Cutover Checklist
Sample Workload Migration / Cutover Checklist
Task # | Task / Subtask Detail | Team | Task Lead /Contact Info | Task Notes & Comments | Est. Duration | Est. Start | Est. End | Actual Start | Actual End | Results / Notes for Post-Change Triage
1 | Migration group team member kickoff / planning call | Migration Team
2 | Verify prerequisites are completed | Migration Team/Client
2.1 | Take backups of on-prem machines | Client DB Team
2.2 | VNETs created and DNS configured to point at new Azure DCs | Client Network Team
2.3 | NSGs created and applied | Client Network Team
2.4 | Network landing information documented per server in the spreadsheet | Client Network Team
2.5 | Firewall rules in place and tested if possible | Client Network Team
2.6 | App Gateways or front end LB built and configured - Backend pools / listeners / rules | Client Network Team
2.7 | Certificates installed on front end | Client Team
2.8 | Landing Resource Groups created and documented per workload/server | Migration Team
2.9 | Landing Availability Groups created and documented per workload/server
2.10 | Service endpoints configured if required | Migration Team
2.11 | ASR Target server configurations verified | Migration Team
2.12 | Assign static IPs to target servers configurations, if applicable | Migration Team
2.13 | Failover testing has been completed | Client Team/Migration Team
2.14 | Failover and post failover plans created in Azure and reviewed | Migration Team
2.15 | Seek Change Request approval and define cutover window | Client Team
2.16 | Schedule App/DBA team support for the cutover activities | Client Team |  |  |  | At least 3 days prior
2.17 | Send first communication | Client Team |  |  |  | 1-2 weeks prior
2.18 | Send second communication | Client Team |  |  |  | 2 days -1 week prior
2.19 | Bypass/modify policy for failed over machines | Client Team
3 | Send final communication | Client Team |  |  |  | Day of window
4 | Validate replication and proper RPO target is being met | Migration Team
Cutover Window Start
5 | Start migration meeting | Migration Team/Client
5.1 | Verify necessary parties are present needed to proceed | Migration Team/Client
5.2 | Send notification if necessary | Client Team
6 | Verify prerequisites are completed | Migration Team/Client
6.1 | Verify backups are complete, if applicable | Client Infrastructure Team
7 | Execute ASR failover | Migration Team
8 | Validate on-prem servers are shut down | Client Infrastructure Team
9 | Conduct functional server validation tests | Migration Team/Client
9.1 | Verify clean boot | Migration Team/Client
9.2 | Verify network connectivity | Migration Team/Client
9.3 | Verify name resolution | Migration Team/Client
10 | Individual Server Validation | Client Infrastructure Team
10.1 | Test RDP/SSH to servers | Client Infrastructure Team
10.2 | Validate Server Ceritificate, if Applicable | Client Infrastructure Team
10.3 | Network Connectivity Test to other migrated resources, DB etc | Client Infrastructure Team
10.4 | Verify File Shares
11 | Update / Validate App Gateway / LB Certificate | Client Network Team
12 | Update / Validate AG or Load Balancer Pools and Check Health | Client Network Team
13 | Update / Validate DNS Changes | Client Infrastructure Team
14 | App Config Changes & Validation | Client Infrastructure Team
14.1 | Update DB Connection String in Config File | Client Infrastructure Team
14.2 | App Services Start/Restart
14.3 | Validate IIS Settings | Client Infrastructure Team
15 | Conduct functional application validation tests | Client Application Team
15.1 | Application Functionality Test in IIS | Client Infrastructure Team
15.2 | Application Load Test | Client Infrastructure Team
16 | Receive final confirmation from all testers | Migration Team/Client
Proceed / Rollback Decision
17 | Windows VMs - Enable serial console bcdedit /ems '{current}' ON bcdedit /emssettings EMSPORT:1 EMSBAUDRATE:115200 | Client Infrastructure Team
18 | Windows VMs - Verify the temporary drive is online in the OS | Client Infrastructure Team
19 | Windows VMs - Move the PageFile to the temporary drive Set-ItemProperty -Path 'HKLM:\SYSTEM\CurrentControlSet\Control\Session Manager\Memory Management' -name "PagingFiles" -Value "D:\pagefile.sys" -Type MultiString -force | Client Infrastructure Team
20 | Setup Operations | Migration Team
20.1 | Install MMA and any needed additional extensions on migrated servers | Migration Team
20.2 | Enable Monitoring | Migration Team
20.3 | Enable Backups | Migration Team
20.4 | Verify the servers are members of a patching schedule | Migration Team
21 | Reboot the VM to apply up the serial and pagefile changes | Client Infrastructure Team
22 | Add proper tags to the VMs | Migration Team |  |  | 0:05
23 | Update Monitoring | Client Team |  |  | 0:10
24 | Send out completion notice | Client Team |  |  | 0:05
25 | Uninstall Mobility service from Azure servers if necessary | Client Team |  |  | 0:30
Cutover Window End
26 | Post migration Application benchmark testing (if applicable) | Client Application Team
27 | Follow up with app and business owners | Migration Team/Client
28 | Debrief and capture lessons learned | Migration Team