## Slide 1: A high-level view of The 10M Migration Process

## Slide 2: Migration Process
Landing Zone
Discover
Migrate
Manage, Optimize, Secure
Pilot
Evaluate current landing zone, or prepare the landing zone
Provide recommendations on any findings
Remediate where needed
Migration Tooling Setup (ASR)
Migrate pilot server group or workload
Learn your environment
Establish build processes
Fine-tune processes
Begin Discovery
Prioritize migration workloads and align to phases
Workload analysis and architecture deep dive
Assess workload for cloud readiness
Identify migration strategy for each workload
Adjust initial migration plan, if needed
Schedule migration with the CMC
Replicate the workloads to the target Azure regions
Perform failover testing
Cutover the workloads to the target Azure regions
Perform post-failover setup for the workload and handoff to 10th Magnitude’s Managed Services
Managed operations
Optimize migrated workloads
Secure migrated workloads
10M Cloud Migration Center
10M Managed Services
10M & Customer Project Team
10M Cloud Migration Center
Continuous Discovery and Migration

## Slide 3
Group n
Migration
Group n
Discovery
Group 2 Discovery
Group 1 - Pilot Migration
Group 3 Discovery
Group 2 Migration
Group 1 - Pilot Discovery
Migration Center
Sprint - 1 Week
Migration Leadership Team Sprint - 2 Weeks
Ongoing Work
Discovery
Meet with workload owners and stakeholders to gather information, dependencies, timeline and build a plan for migrating the workload or workload group.
Migration Group 1 - Pilot
Identify a low impact workload for tooling and process testing
Conduct a migration to demonstrate and fine tune tooling, process, plans
Start discovery for the next migration group
Migration Groups 2+
The 10M Migration Center will replicate and perform cutover on groups of workloads
Perform testing to verify the workload meets customer standards
Transition
Transition the workload to 10M Managed Services
Provide documentation
Repeat
Cycle through the process to quickly migrate groups of servers and workloads
Continuous Discovery and Migration
Sample Migration Cycle
Landing Zone Assessment and Preparation
Migration Leadership Team
Managed Services
Cloud Migration Center
Week 1
Week 2
Week 3
Week 4
Week 5+

## Slide 4: Migration Tooling
10M Recommends Azure Site Recovery (ASR) for large scale migrations
We will review your VMM/vSphere topology and migration targets, and build an efficient migration tooling topology
We will review any existing Azure native migration tooling and utilize where possible, if desired