## Server List
Migration Group | Workload Name | Server Name | Environment | IP | Server OS | Description | Migration Target | Migration Method | Migration Status | New Server Name (if changing during migration) | Landing Resource Group | Landing VNET | Landing Subnet | Landing Availability Set | Current Location | Third Party Support | Risks / Dependencies | Recommended VM Series (if not using ASR default) | Recommended Disks (if not using ASR default) | Additional Notes
1 | App01 | Server01 | TST | 10.1.1.1 | Windows 2016 | Some corp testing app. | Migrate | ASR | Replicating | Retain Existing | rgp01 | vnet01 | vnet01-defaultsnet | Not Needed | DC01 |  |  | A2_v2 | Standard
2 | App02 | Server02 | STG | 10.1.1.2 | Windows 2008R2 | Some corp staging app. | Migrate | Net New Azure |  | Retain Existing | rgp02 | vnet02 | vnet02-defaultsnet | app02-as | DC01 |  | Needs app reconfiguration for updated IP.
3 | App03 | Server03 | PRD | 10.1.13 | Red Hat 7.6 | Some super critical prd app. | Migrate | ASR |  | Retain Existing | rgp03 | vnet03 | vnet03-defaultsnet | app03-as | DC02