Azure Cloud Migration Solution

Process Overview

Cognizant Microsoft Business Group

20 North Wacker Drive #530

Chicago, IL 60606

Notice of Confidentiality  	©2021 Cognizant Microsoft Business Group All rights reserved.

IS SUBJECT TO THE TERMS OF THE COGNIZANT MICROSOFT BUSINESS GROUP NON-DISCLOSURE AGREEMENT. NEITHER THIS DOCUMENT NOR ITS CONTENTS MAY BE REVEALED OR DISCLOSED TO UNAUTHORIZED PERSONS OR SENT OUTSIDE THE AFOREMENTIONED COMPANY WITHOUT PRIOR PERMISSION FROM COGNIZANT MICROSOFT BUSINESS GROUP.

Table of Contents

Summary	3

Migration Solution Delivery	4

Phase 1: Project Setup	5

Stakeholders during Project Setup	5

Tasks and Responsibilities during Project Setup	5

Phase 2: Workload Discovery and Solution Design	6

Stakeholders during Workload Discovery and Solution Design	6

Tasks and responsibilities during Workload Discovery and Solution Design:	6

Phase 3: Landing Zone Preparation	7

Stakeholders during Landing Zone Preparation	7

Sub-Phases / Milestones of Landing Zone Preparation	7

Tasks and responsibilities during Landing Zone Preparation	7

Phase 4: Migration	8

Stakeholders during Migration	8

High-level Phases and Milestones of a Migration	8

Migration Planning	9

The Lifecycle of a Workload Migration	10

The Continuous Discovery and Migration Model	10

Tasks and Responsibilities during Migration	11

Phase 5: Project Closeout	12

Stakeholders during Project Closeout	12

Tasks and Responsibilities during Project Closeout	12

Translating the Phases to an Azure Devops Project	13

Azure DevOps Project Structure	13

Communication Standards	14

Communication Mediums	14

Meeting Structure	14

Documentation Standards	15

# Summary

This document describes the proposed Azure Cloud Migration Solution and its framework used to deliver a customer project utilizing a streamlined phased process. Using this approach is designed to aid with workstream management by adapting to an Agile project management style using Azure DevOps, repeatable expected results, and streamlined transition between different teams and business units. The Azure DevOps project framework is intended to enable assigning underlying tasks to multiple teams while maintaining proper project visibility and oversight for the project management team.

# Migration Solution Delivery

To streamline the work associated with a large migration, the migration is split into phases. This allows us to carve up workstreams and assign them to the proper program managers and underlying teams. A migration project consists of 5 high-level phases. The phases are as follows and fit into the overall Delivery Management framework as illustrated.

- Project Setup

- Landing Zone Discovery and Design/Remediation

- Landing Zone Preparation

- Migration

- Project Closeout

Delivery Process and Resourcing

Execution Flow

## Phase 1: Project Setup

| Inputs | Outputs |
| --- | --- |
| - Customer information and details from CEA / Sales and workshops, for example: project sizing - Welcome kit / documentation / diagrams - Greenfield or brownfield landing zone determination | - Completed welcome kit - All access and information needed to start discovery - All prequisite tooling planned and deployed – Azure Migrate / ASR Deployment Planner - Project framework – DevOps project, internal and externally facing SharePoint sites, internal and externally facing Teams channel - Scheduled meetings |

### Stakeholders during Project Setup

- Delivery Director

- Delivery Manager

- Principal Architect

- Infrastructure Architect

- Infrastructure Engineer(s)

- Customer’s Project Management Resource(s)

### Tasks and Responsibilities during Project Setup

| Task | 10M Responsibility | Customer Responsibility |
| --- | --- | --- |
| Handoff meeting from Sales Team to Delivery Team | Execute |  |
| Initial Communication |  |  |
| Customer communication, schedule kick-off meeting and initial design sessions | Execute and communicate |  |
| Send Welcome Kit, gather documentation | Initiate | Provide |
| Communication Channel Setup |  |  |
| Create internal/external SharePoint sites | Execute and communicate |  |
| Create internal/external MS Teams channels | Execute and communicate |  |
| DevOps Project Setup |  |  |
| Create organization for the customer | Execute and communicate |  |
| Deploy the VDC project and backlog | Execute and communicate |  |
| Customize the DevOps project | Execute |  |
| Initial Access and Tooling Setup |  |  |
| Customer Azure subscription details and necessary access | Initiate | Provide |
| Additional access as required – on-prem vSphere, server or environment administrative accounts | Initiate | Provide |
| Install Azure Migrate or ASR Deployment Planner and run assessments for migration planning | Execute, collaborate | Collaborate |
| Ongoing Project Management |  |  |
| Schedule regular project meetings | Execute and communicate | Collaborate |

## Phase 2: Workload Discovery and Solution Design

| Inputs | Outputs |
| --- | --- |
| - Completed welcome kit - Relevant documentation / diagrams - Design sessions for the following topics: - Organization Structure, Governance - Identity - Workloads - Network - Operations | - Compiled relevant information from welcome kit / documentation and design sessions: - Completed questionnaire from each design session - Existing environment overview - Workload requirements - Deployment process overview and guidelines - Change control guidelines - Design recommendations and completed documents for each design session topic - Cloud Worksheet - Customer resource(s) assigned to assist with deployment (if applicable) |

### Stakeholders during Workload Discovery and Solution Design

- Delivery Manager

- Principal Architect

- Infrastructure Architect / Lead

- Infrastructure Engineer(s)

- Customer’s Project Management Resource(s)

- Customer’s IT staff, preferably the following roles:

  - Cloud Architect

  - Senior Network Engineer

  - Senior Systems Engineer

  - Senior Security Engineer

  - Operations Lead

### Tasks and responsibilities during Workload Discovery and Solution Design:

| Task | 10M Responsibility | Customer Responsibility |
| --- | --- | --- |
| Cloud design sessions (onsite preferred) | Initiate and collaborate | Collaborate |
| Discovery and requirements gathering | Initiate and collaborate | Collaborate |
| Environment design | Execute and collaborate | Collaborate |
| Deployment and migration planning | Execute and collaborate | Collaborate |
| Licensing review with the customer | Execute and collaborate | Collaborate |
| Create design and recommendations documents, workload migration planning – groupings, server lists | Execute and collaborate | Collaborate |
| Ongoing Communication |  |  |
| Schedule deep dive and review sessions with workload owners and SMEs | Execute and communicate | Collaborate |

## Phase 3: Landing Zone Preparation

| Inputs | Outputs |
| --- | --- |
| - Design documents - Cloud Worksheet - Managed | - VDC Landing zone deployed in Azure - Managed Services onboarded - Operations foundation configured |

### Stakeholders during Landing Zone Preparation

- Delivery Manager

- Principal Architect

- Infrastructure Architect / Lead

- Infrastructure Engineer(s)

- Customer’s Project Management Resource(s)

- Customer’s IT staff, preferably the following roles:

  - Cloud Architect

  - Senior Network Engineer

  - Senior Systems Engineer

  - Senior Security Engineer

  - Operations Lead

### Sub-Phases / Milestones of Landing Zone Preparation

The Landing Zone Preparation is roughly defined in 6 sub-phases. Each of these should align to a feature and completion will be marked as a milestone in the overall migration execution phase.

- Governance and Core Scaffolding

- Networking Setup

- Identity Setup

- Workload / Template Setup

- Managed Services Onboarding, if applicable

- Operations Setup by Managed Services, if applicable

### Tasks and responsibilities during Landing Zone Preparation

| Task | 10M Resources | 10M Responsibility | Customer Resources | Customer Responsibility |
| --- | --- | --- | --- | --- |
| Complete Cloud Design Worksheet | Project Architect/Lead | Execute | - |  |
| Deploy and personalize landing zone (VDC) | Project Architect/Lead Infra Engineer CMC | Execute and collaborate | Infra Team | Collaborate |
| Setup operations foundation | Project Architect/Lead Infra Engineer CMC | Execute and collaborate | Infra Team | Collaborate |
| Manged Services onboarding, if applicable | MS | Execute and collaborate | PM/Infra Team | Collaborate |
| Ongoing Communication |  |  |  |  |
| Continued sessions with workload owners to develop migration planning. | DD/DM Project Architect/Lead | Execute and collaborate | PM/Infra/App Teams | Collaborate |

## Phase 4: Migration

| Inputs | Outputs |
| --- | --- |
| - Welcome Kit - Migration Plan - Workload and server groupings - Migration group schedule that includes lifecycle for each group – discovery, replication, test cutover, cutover. - Workload Information (Migration Worksheet) - Migration prerequisites - Detailed source and landing zone information - Workload owners and contacts | - Functional VDC - Functional workloads - Documentation, lessons learned |

### Stakeholders during Migration

- Delivery Manager

- Principal Archtect

- Infrastructure Architect / Lead

- Infrastructure Engineer(s)

- Customer’s staff, preferably the following roles:

  - Project Manager

  - Cloud Architect

  - Senior Network Engineer

  - Senior Systems Engineer

  - Senior Security Engineer

  - Operations Lead

### High-level Phases and Milestones of a Migration

Migration execution can be broken down into the following sub-phases.

- Migration Tooling Setup – Setup ASR or Azure Migrate. Work with the customer to provide a design that meets their needs and then deploy.

- Up-front Planning and Discovery – Perform pilot and initial workload discovery, prioritize, estimate timelines and schedule migrations.

- Perform a Pilot Migration – Identify a low impact workload to migrate for tooling and process testing and demonstration. Start discovery of the next workload group.

- Continuous Discovery and Migration

  - Perform discovery on the workload(s) in the group. Compile prerequisistes and workload information and formulate a plan and timeline. When complete, begin discovery on the next workload or group.

  - Replicate the Servers in the Workload – Install any necessary agents and establish replication.

  - Perform Failover Testing – Perform isolated failover testing to verify the servers boot and perform as expected in Azure.

  - Cutover – Cut over the workloads to Azure and perform any post-failover configuration.

  - Validation and Handoff – Provide support for the customer while they validate workload functionality and performance. Obtain customer signoff that the migration is complete and hand off to the customer or Managed Services for ongoing operational support.

  - Repeat the steps for the next workload or group until all workloads have been migrated.

- Cleanup – Remove any migration tooling components when migrations are complete, if requested.

### Migration Planning

Migration planning consists of all planning and scheduling activities, including:

- Working the customer to establish a pace at which their organization can migrate. Many factors should be considered, such as application knowledge and resource availability, workload business criticality, complexity, maintenance window availability, circuit speeds, change control process, etc. For example, if their internet circuit only supports replicating 40 servers per week, we should plan to migrate just under that if possible.

- Working with the customer to identify workloads and when the best time to migrate those workloads would be.

- Creating a high level schedule that is at least 2-3 weeks out. This plan should go out as far in advance as possible. This will allow for proper resource planning and business notification, as well as allowing for some change without affecting the overall project timeline.

Sample Migration Plan Timeline View

### The Lifecycle of a Workload Migration

Discovery, replication, failover testing, failover, and handoff make up the lifecycle of a workload or workload group migration. Each workload or workload group lifecycle is tracked in the CMC DevOps backlog and should also be tracked in the Migration Plan as well as any RAID items in a RAID Log. The lifecycle duration will vary from workload to workload depending on the complexity and size (amount of servers) within the workload.

### The Continuous Discovery and Migration Model

The goal of continuos discovery and migration is to accelerate migrations by creating a repeatable cycle in which discovery can be completed in parallel to migrations. This model allows for fast and efficient migrations and is best suited for large migrations or migrations with timeline constraints.

To start continuous discovery and migration – the first workload discovery is completed by the project lead or business analyst. As soon as discovery is complete, workload is handed off to the CMC to begin migration activites. While the CMC is migrating the workload, the project team moves on to discover the next workload. This process repeats until all workloads are migrated. In order for the process to be successful, there must be a clear path forward and workloads must be ready for discovery and migration when resources are available. The example below depicts the process. The sprint and timeline per workload may vary depending on the complexity and number of servers in the group.

### Tasks and Responsibilities during Migration

| Task | 10M Resources | 10M Responsibility | Customer Resources | Customer Responsibility |
| --- | --- | --- | --- | --- |
| Tooling Setup |  |  |  |  |
| Install and configure migration tooling, tooling support | CMC / Migration Team | Execute and collaborate | Infra Team | Execute and collaborate |
| Workload Onboarding |  |  |  |  |
| Migration planning – grouping, establish lifecycle timeline for each workload | DD/DM Project Architect/Lead | Execute and collaborate | PM Team | Collaborate |
| Workload cloud licensing review | Project Architect/Lead | Collaborate | PM/Infra Team | Execute and collaborate |
| Ongoing workload discovery | Project Architect/Lead Business Analyist | Execute and collaborate | PM/Infra/App Teams | Collaborate |
| Complete Migration Worksheet for workload groups | Project Architect/Lead | Execute and collaborate | - |  |
| Establish replication of workloads | CMC / Migration Team | Execute and collaborate | Infra Team | Collaborate |
| Configure alerts on Site Recovery events in each Recovery Services Vault | CMC / Migration Team | Execute and collaborate | - |  |
| Complete workload failover testing | CMC / Migration Team | Execute and collaborate | Infra/App Teams | Collaborate |
| Cutover |  |  |  |  |
| Cutover workload groups | CMC / Migration Team | Execute and collaborate | PM/Infra/App Teams | Collaborate |
| Validate workloads | CMC / Migration Team | Execute and collaborate | Infra/App Teams | Execute and collaborate |
| Transition workloads to Managed Services after cutover | CMC / Migration Team | Execute and collaborate | - |  |
| Cleanup – remove mobility agents, decommission ASR components, etc | CMC / Migration Team | Execute and collaborate | Infra Team | Execute and collaborate |
| Customer signoff | DD/DM Project Architect/Lead | Collaborate | PM/Infra/App Teams | Execute and collaborate |

## Phase 5: Project Closeout

| Inputs | Outputs |
| --- | --- |
| - Completed VDC - Completed migration - Completed documentation | - Documentation package - Useful artifacts and lessons learned - Satisfied customer |

### Stakeholders during Project Closeout

- Delivery Director

- Delivery Manager

- Infrastructure Architect / Lead

- Customer’s Project Management Resource(s)

### Tasks and Responsibilities during Project Closeout

| Task | 10M Responsibility | Customer Responsibility |
| --- | --- | --- |
| Customer communication | Initiate | Collaborate |
| Project sign off | Initiate | Execute |
| Remaining documentation delivery to customer | Execute |  |

# Translating the Phases to an Azure Devops Project

Using a phased approach enables us to easily rationalize the workstreams and translate them to a repeatable DevOps project based on the Agile framework. Below is an example of how the hierarchy of a DevOps project would look for a typical customer migration project.

### Azure DevOps Project Structure

- Each customer will have its own organization created in Azure DevOps to separate from 10M’s internal org.

- Each customer project will be created as a separate new project in their Azure DevOps organization. This allows us to separate multiple initiatives or reference past projects for the customer.

- Each project will have teams created that are focused on a specific backlog – for example the VDC team members will have a backlog specific to VDC activities.

- Each project should have an Epic for each major project phase containing a hierarchy of all the milestones and work items.

- Each subphase should align to a feature with larger milestones aligning to stories with subtasks.

- Specific tasks should be nested in the user stories for assignment to engineers actually doing the work.

- Sprints are 2 week blocks. Aligning work to sprints is completed in a planning meeting the week prior to the start of a new sprint.

- Each project will have one or more repos for builds. The repos should be cloned from master template repos.

- Any project related artifacts that were used or developed during the project – like ARM templates, scripts, custom configurations, etc should be uploaded to the project repos.

# Communication Standards

In efforts to ensure we are consistent in the way we communicate among the team and with customers, below is a breakdown of the communication standards and meeting structure.

### Communication Mediums

10th Magnitude’s internal Microsoft Teams instance is the preferred method of ad-hoc communication, meetings, and design sessions. During project setup, 2 teams channels are created for communication – an externally facing channel for direct customer communication and file sharing, and an internal only channel for internal team collaboration and file sharing. Email is ok too, just be sure to copy the project team on communications for awareness.

### Meeting Structure

| Meeting | Visibility | Frequency | Duration | Agenda |
| --- | --- | --- | --- | --- |
| On-Site Kickoff | External | One Time | 1-3 Days | Engagement Introduction Discovery sessions Stakeholder Review |
| Sprint Planning | External | Every 2 weeks - week prior to planned sprint | 30-60 min | Planning work for the upcoming sprint Review work completed and move any remaining work from the previous sprint to the current sprint. |
| Project Status | External | 1-2 per Week (depends on project size/complexity/customer working abilities) | 1-2 hours | Get updates from each group on progress and work completed Discuss next steps for a timeframe Discuss resources and time allotment Work through blockers |
| Stakeholder Review | External | Every 2 weeks | 30 min | Executive updates on project status Discuss blockers |
| Working Sessions | External | As Needed | 1-2 hours | Sessions with the customer's teams for additional technical deep-dive discovery or completing work items |
| Internal Sync | Internal | Weekly | 30 min | Discuss project and blockers Develop and discuss strategy |

# Documentation Standards

In efforts to ensure everyone can find the information that is needed when its needed, below is a breakdown of where each type of documentation should be stored.

| Document | Location |
| --- | --- |
| Sales / Marketing material, presentations, templates | SharePoint DCT Catalog |
| SoW Templates | SharePoint DCT Catalog |
| Customer checklists, questionnaire templates | SharePoint DCT Catalog |
| Delivery templates – Migration worksheet | SharePoint DCT Catalog |
| Public Shareable Technical Documentation / Guides | SharePoint DCT Catalog |
| Customer project related deployment templates, scripts | Related customer DevOps project artifacts |
| Customer project related technical documents | SharePoint |
| DCT/CMC/MS team IP and how-to documentation | DevOps Wiki |
| Base deployment templates, useful scripts, examples | DevOps Wiki |