## Project Info
Client Name | Relativity
Project Name | Azure Transformation & Migration - 08/23/2019
Project Start Date | 2019-08-26

## Project Planner
Relativity - Azure Transformation & Migration - 08/23/2019 | [13 empty] | Labor Day | [34 empty] | Relativity Fest | Relativity Fest | Relativity Fest | [25 empty] | Thanksgiving | Thanksgiving | [17 empty] | Christmas |  |  |  |  | New Years
ID | FEATURES | Milestone | Client Work | D | START | END | DUR. |  | 2019-08-26 |  |  |  |  | 2019-09-02 |  |  |  |  | 2019-09-09 |  |  |  |  | 2019-09-16 |  |  |  |  | 2019-09-23 |  |  |  |  | 2019-09-30 |  |  |  |  | 2019-10-07 |  |  |  |  | 2019-10-14 |  |  |  |  | 2019-10-21 |  |  |  |  | 2019-10-28 |  |  |  |  | 2019-11-04 |  |  |  |  | 2019-11-11 |  |  |  |  | 2019-11-18 |  |  |  |  | 2019-11-25 |  |  |  |  | 2019-12-02 |  |  |  |  | 2019-12-09 |  |  |  |  | 2019-12-16 |  |  |  |  | 2019-12-23 |  |  |  |  | 2019-12-30 |  |  |  |  | 2020-01-06 |  |  |  |  | 2020-01-13 |  |  |  |  | 2020-01-20 |  |  |  |  | 2020-01-27 |  |  |  |  | 2020-02-03 |  |  |  |  | 2020-02-10 |  |  |  |  | 2020-02-17
 | time axis 2019-08-26 to 2020-02-21
1 | Contributor rights to Azure subcription(s) granted | ü | û |  | 2019-09-03 | 2019-03-10 | -127 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-03 | 2019-03-11 | -127 | Actual | bar: 2019-08-26 to 2020-02-21
2 | Service Principal Account setup | ü | û |  | 2019-09-03 | 2019-08-30 | -3 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-03 | 2019-08-30 | -3 | Actual | bar: 2019-08-26 to 2020-02-21
3 | Review | ü | û | 4 | 2019-09-03 | 2019-09-13 | 9 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-03 | 2019-09-13 | 9 | Actual | bar: 2019-08-26 to 2020-02-21
4 | Initial Delivery Plan |  |  | 5 | 2019-08-26 | 2019-08-30 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-08-26 | 2019-08-30 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
5 | Workload dependancy Analysis ( ASR deployment Planner & Dependancy Mapper ) |  |  | 8 | 2019-09-03 | 2019-09-13 | 9 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-03 | 2019-09-13 | 9 | Actual | bar: 2019-08-26 to 2020-02-21
6 | Workload priritization |  |  | 6 | 2019-09-09 | 2019-09-24 | 12 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-09 | 2019-09-24 | 12 | Actual | bar: 2019-08-26 to 2020-02-21
7 | Engagement Preparation |  |  |  | 2019-09-09 | 2019-09-24 | 12 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-09 | 2019-09-24 | 12 | Actual | bar: 2019-08-26 to 2020-02-21
8 | Project Kick-off | ü |  |  | 2019-09-25 | 2019-09-25 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-25 | 2019-09-25 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
9 | VDC Remediation |  |  |  | 2019-09-30 | 2019-10-25 | 20 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-30 | 2019-10-25 | 20 | Actual | bar: 2019-08-26 to 2020-02-21
9 | Phase 1: Migration Groups 1-6 |  |  |  | 2019-09-30 | 2019-11-11 | 31 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-30 | 2019-11-11 | 31 | Actual | bar: 2019-08-26 to 2020-02-21
10 | Migration Group 1 (Pilot) |  |  |  | 2019-09-30 | 2019-10-14 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-30 | 2019-10-14 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
11 | Prepare Migration Group worksheet |  |  |  | 2019-09-30 | 2019-10-03 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-09-30 | 2019-10-03 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
12 | Submit Workload Migration ticket |  |  |  | 2019-10-04 | 2019-10-04 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-04 | 2019-10-04 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
13 | Perform Cut over |  |  |  | 2019-10-07 | 2019-10-11 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-07 | 2019-10-11 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
14 | Conduct Acceptance Testing |  | û |  | 2019-10-11 | 2019-10-11 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-11 | 2019-10-11 |  | Actual | bar: 2019-08-26 to 2020-02-21
15 | Migration Sign off | ü | û |  | 2019-10-14 | 2019-05-17 |  | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-14 | 2019-05-17 |  | Actual | bar: 2019-08-26 to 2020-02-21
16 | Migration Group 2 |  |  |  | 2019-10-07 | 2019-10-21 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-07 | 2019-10-21 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
17 | Prepare Migration Group worksheet |  |  |  | 2019-10-07 | 2019-10-10 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-07 | 2019-10-10 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
18 | Submit Workload Migration ticket |  |  |  | 2019-10-11 | 2019-10-11 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-11 | 2019-10-11 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
19 | Perform Cut over |  |  |  | 2019-10-14 | 2019-10-18 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-14 | 2019-10-18 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
20 | Conduct Acceptance Testing |  | û |  | 2019-10-18 | 2019-10-18 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-18 | 2019-10-18 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
21 | Migration Sign off | ü | û |  | 2019-10-24 | 2019-05-17 |  | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-24 | 2019-05-17 |  | Actual | bar: 2019-08-26 to 2020-02-21
22 | Migration Group 3 |  |  |  | 2019-10-14 | 2019-10-28 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-14 | 2019-10-28 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
23 | Prepare Migration Group worksheet |  |  |  | 2019-10-14 | 2019-10-17 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-14 | 2019-10-17 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
24 | Submit Workload Migration ticket |  |  |  | 2019-10-18 | 2019-10-18 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-18 | 2019-10-18 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
25 | Perform Cut over |  |  |  | 2019-10-21 | 2019-10-25 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-21 | 2019-10-25 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
26 | Conduct Acceptance Testing |  | û |  | 2019-10-25 | 2019-10-25 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-25 | 2019-10-25 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
27 | Migration Sign off | ü | û |  | 2019-10-28 | 2019-05-17 | -117 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-28 | 2019-05-17 | -117 | Actual | bar: 2019-08-26 to 2020-02-21
28 | Migration Group 4 |  |  |  | 2019-10-21 | 2019-11-04 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-21 | 2019-11-04 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
29 | Prepare Migration Group worksheet |  |  |  | 2019-10-21 | 2019-10-24 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-21 | 2019-10-24 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
30 | Submit Workload Migration ticket |  |  |  | 2019-10-25 | 2019-10-25 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-25 | 2019-10-25 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
31 | Perform Cut over |  |  |  | 2019-10-28 | 2019-11-01 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-28 | 2019-11-01 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
32 | Conduct Acceptance Testing |  |  |  | 2019-11-01 | 2019-11-01 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-01 | 2019-11-01 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
33 | Migration Sign off | ü | û |  | 2019-11-04 | 2019-05-17 | -122 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-04 | 2019-05-17 | -122 | Actual | bar: 2019-08-26 to 2020-02-21
34 | Migration Group 5 |  |  |  | 2019-10-28 | 2019-11-11 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-28 | 2019-11-11 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
35 | Prepare Migration Group worksheet |  |  |  | 2019-10-28 | 2019-10-31 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-10-28 | 2019-10-31 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
36 | Submit Workload Migration ticket |  |  |  | 2019-11-01 | 2019-11-01 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-01 | 2019-11-01 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
37 | Perform Cut over |  |  |  | 2019-11-04 | 2019-11-08 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-04 | 2019-11-08 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
38 | Conduct Acceptance Testing |  | û |  | 2019-11-08 | 2019-11-08 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-08 | 2019-11-08 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
39 | Migration Sign off | ü | û |  | 2019-11-11 | 2019-05-17 | -127 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-11 | 2019-05-17 | -127 | Actual | bar: 2019-08-26 to 2020-02-21
46 | Phase 2: Migration Groups 6-9 |  |  |  | 2019-11-04 | 2019-12-16 | 31 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-04 | 2019-12-16 | 31 | Actual | bar: 2019-08-26 to 2020-02-21
40 | Migration Group 6 |  |  |  | 2019-11-04 | 2019-11-18 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-04 | 2019-11-18 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
41 | Prepare Migration Group worksheet |  |  |  | 2019-11-04 | 2019-11-07 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-04 | 2019-11-07 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
42 | Submit Workload Migration ticket |  |  |  | 2019-11-08 | 2019-11-08 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-08 | 2019-11-08 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
43 | Perform Cut over |  |  |  | 2019-11-11 | 2019-11-15 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-11 | 2019-11-15 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
44 | Conduct Acceptance Testing |  | û |  | 2019-11-14 | 2019-11-15 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-14 | 2019-11-15 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
45 | Migration Sign off | ü | û |  | 2019-11-18 | 2019-05-17 | -132 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-18 | 2019-05-17 | -132 | Actual | bar: 2019-08-26 to 2020-02-21
47 | Migration Group 7 |  |  |  | 2019-11-11 | 2019-11-25 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-11 | 2019-11-25 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
48 | Prepare Migration Group worksheet |  |  |  | 2019-11-11 | 2019-11-14 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-11 | 2019-11-14 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
49 | Submit Workload Migration ticket |  |  |  | 2019-11-15 | 2019-11-15 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-15 | 2019-11-15 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
50 | Perform Cut over |  |  |  | 2019-11-18 | 2019-11-22 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-18 | 2019-11-22 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
51 | Conduct Acceptance Testing |  |  |  | 2019-11-21 | 2019-11-22 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-21 | 2019-11-22 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
52 | Migration Sign off | ü | û |  | 2019-11-25 | 2019-05-17 | -137 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-25 | 2019-05-17 | -137 | Actual | bar: 2019-08-26 to 2020-02-21
53 | Migration Group 8 |  |  |  | 2019-11-18 | 2019-12-09 | 16 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-18 | 2019-12-09 | 16 | Actual | bar: 2019-08-26 to 2020-02-21
54 | Prepare Migration Group worksheet |  |  |  | 2019-11-18 | 2019-11-21 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-18 | 2019-11-21 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
55 | Submit Workload Migration ticket |  |  |  | 2019-11-22 | 2019-11-22 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-11-22 | 2019-11-22 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
56 | Perform Cut over |  |  |  | 2019-12-02 | 2019-12-06 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-02 | 2019-12-06 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
57 | Conduct Acceptance Testing |  |  |  | 2019-12-05 | 2019-12-06 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-05 | 2019-12-06 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
58 | Migration Sign off | ü | û |  | 2019-12-09 | 2019-12-09 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-09 | 2019-05-17 | -147 | Actual | bar: 2019-08-26 to 2020-02-21
59 | Migration Group 9 |  |  |  | 2019-12-02 | 2019-12-16 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-02 | 2019-12-16 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
60 | Prepare Migration Group worksheet |  |  |  | 2019-12-02 | 2019-12-05 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-02 | 2019-12-05 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
61 | Submit Workload Migration ticket |  |  |  | 2019-12-06 | 2019-12-06 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-06 | 2019-12-06 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
62 | Perform Cut over |  |  |  | 2019-12-09 | 2019-12-13 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-09 | 2019-12-13 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
63 | Conduct Acceptance Testing |  |  |  | 2019-12-12 | 2019-12-13 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-12 | 2019-12-13 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
64 | Migration Sign off | ü | û |  | 2019-12-16 | 2019-05-17 | -152 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-16 | 2019-05-17 | -152 | Actual | bar: 2019-08-26 to 2020-02-21
83 | Phase 3: Migration Groups 10-13 |  |  |  | 2019-12-09 | 2020-01-20 | 31 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-09 | 2020-01-20 | 31 | Actual | bar: 2019-08-26 to 2020-02-21
65 | Migration Group 10 |  |  |  | 2019-12-09 | 2019-12-23 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-09 | 2019-12-23 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
66 | Prepare Migration Group worksheet |  |  |  | 2019-12-09 | 2019-12-12 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-09 | 2019-12-12 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
67 | Submit Workload Migration ticket |  |  |  | 2019-12-13 | 2019-12-13 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-13 | 2019-12-13 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
68 | Perform Cut over |  |  |  | 2019-12-16 | 2019-12-20 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-16 | 2019-12-20 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
69 | Conduct Acceptance Testing |  |  |  | 2019-12-19 | 2019-12-20 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-19 | 2019-12-20 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
70 | Migration Sign off | ü | û |  | 2019-12-23 | 2019-05-17 | -157 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2019-12-23 | 2019-05-17 | -157 | Actual | bar: 2019-08-26 to 2020-02-21
71 | Migration Group 11 |  |  |  | 2020-01-06 | 2020-01-20 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-06 | 2020-01-20 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
72 | Prepare Migration Group worksheet |  |  |  | 2020-01-06 | 2020-01-09 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-06 | 2020-01-09 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
73 | Submit Workload Migration ticket |  |  |  | 2020-01-10 | 2020-01-10 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-10 | 2020-01-10 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
74 | Perform Cut over |  |  |  | 2020-01-13 | 2020-01-17 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-13 | 2020-01-17 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
75 | Conduct Acceptance Testing |  |  |  | 2020-01-18 | 2020-01-19 | 0 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-18 | 2020-01-19 | 0 | Actual | bar: 2019-08-26 to 2020-02-21
76 | Migration Sign off | ü | û |  | 2020-01-20 | 2019-05-17 | -177 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-20 | 2019-05-17 | -177 | Actual | bar: 2019-08-26 to 2020-02-21
77 | Migration Group 12 |  |  |  | 2020-01-13 | 2020-01-27 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-13 | 2020-01-27 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
78 | Prepare Migration Group worksheet |  |  |  | 2020-01-13 | 2020-01-16 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-13 | 2020-01-16 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
79 | Submit Workload Migration ticket |  |  |  | 2020-01-17 | 2020-01-17 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-17 | 2020-01-17 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
80 | Perform Cut over |  |  |  | 2020-01-20 | 2020-01-24 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-20 | 2020-01-24 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
81 | Conduct Acceptance Testing |  |  |  | 2020-01-23 | 2020-01-24 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-23 | 2020-01-24 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
82 | Migration Sign off | ü | û |  | 2020-01-27 | 2019-05-17 | -182 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-27 | 2019-05-17 | -182 | Actual | bar: 2019-08-26 to 2020-02-21
84 | Migration Group 13 |  |  |  | 2020-01-20 | 2020-02-03 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-20 | 2020-02-03 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
85 | Prepare Migration Group worksheet |  |  |  | 2020-01-20 | 2020-01-23 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-20 | 2020-01-23 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
86 | Submit Workload Migration ticket |  |  |  | 2020-01-24 | 2020-01-24 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-24 | 2020-01-24 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
87 | Perform Cut over |  |  |  | 2020-01-27 | 2020-01-31 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-27 | 2020-01-31 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
88 | Conduct Acceptance Testing |  |  |  | 2020-01-30 | 2020-01-31 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-30 | 2020-01-31 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
89 | Migration Sign off | ü | û |  | 2020-02-03 | 2019-05-17 | -187 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-03 | 2019-05-17 | -187 | Actual | bar: 2019-08-26 to 2020-02-21
90 | Migration Group 14 |  |  |  | 2020-01-27 | 2020-02-10 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-27 | 2020-02-10 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
91 | Prepare Migration Group worksheet |  |  |  | 2020-01-27 | 2020-01-30 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-27 | 2020-01-30 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
92 | Submit Workload Migration ticket |  |  |  | 2020-01-31 | 2020-01-31 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-31 | 2020-01-31 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
93 | Perform Cut over |  |  |  | 2020-02-03 | 2020-02-07 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-03 | 2020-02-07 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
94 | Conduct Acceptance Testing |  |  |  | 2020-02-06 | 2020-02-07 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-06 | 2020-02-07 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
95 | Migration Sign off | ü | û |  | 2020-02-10 |  | -31336 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-10 |  | -31336 | Actual | bar: 2019-08-26 to 2020-02-21
96 | Migration Group 15 |  |  |  | 2020-02-03 | 2020-02-17 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-03 | 2020-02-17 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
97 | Prepare Migration Group worksheet |  |  |  | 2020-02-03 | 2020-02-06 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-03 | 2020-02-06 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
98 | Submit Workload Migration ticket |  |  |  | 2020-02-07 | 2020-02-07 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-07 | 2020-02-07 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
99 | Perform Cut over |  |  |  | 2020-02-10 | 2020-02-14 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-10 | 2020-02-14 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
100 | Conduct Acceptance Testing |  |  |  | 2020-02-13 | 2020-02-14 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-13 | 2020-02-14 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
101 | Migration Sign off | ü | û |  | 2020-02-17 |  | -31341 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-17 |  | -31341 | Actual | bar: 2019-08-26 to 2020-02-21
102 | Migration Group 16 |  |  |  | 2020-02-10 | 2020-02-24 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-10 | 2020-02-24 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
103 | Prepare Migration Group worksheet |  |  |  | 2020-02-10 | 2020-02-13 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-10 | 2020-02-13 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
104 | Submit Workload Migration ticket |  |  |  | 2020-02-14 | 2020-02-14 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-14 | 2020-02-14 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
105 | Perform Cut over |  |  |  | 2020-02-17 | 2020-02-21 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-17 | 2020-02-21 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
106 | Conduct Acceptance Testing |  |  |  | 2020-02-20 | 2020-02-21 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-20 | 2020-02-21 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
107 | Migration Sign off | ü | û |  | 2020-02-24 |  | -31346 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-24 |  | -31346 | Actual | bar: 2019-08-26 to 2020-02-21
108 | Migration Group 17 |  |  |  | 2020-02-10 | 2020-02-24 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-10 | 2020-02-24 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
109 | Prepare Migration Group worksheet |  |  |  | 2020-02-10 | 2020-02-13 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-10 | 2020-02-13 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
110 | Submit Workload Migration ticket |  |  |  | 2020-02-14 | 2020-02-14 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-14 | 2020-02-14 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
111 | Perform Cut over |  |  |  | 2020-02-17 | 2020-02-21 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-17 | 2020-02-21 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
112 | Conduct Acceptance Testing |  |  |  | 2020-02-20 | 2020-02-21 | 2 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-20 | 2020-02-21 | 2 | Actual | bar: 2019-08-26 to 2020-02-21
113 | Migration Sign off | ü | û |  | 2020-02-24 |  | -31346 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-24 |  | -31346 | Actual | bar: 2019-08-26 to 2020-02-21
114 | Migration Group 18 |  |  |  | 2020-01-27 | 2020-02-10 | 11 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-27 | 2020-02-10 | 11 | Actual | bar: 2019-08-26 to 2020-02-21
115 | Prepare Migration Group worksheet |  |  |  | 2020-01-27 | 2020-01-30 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-27 | 2020-01-30 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
116 | Submit Workload Migration ticket |  |  |  | 2020-01-31 | 2020-01-31 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-01-31 | 2020-01-31 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
117 | Perform Cut over |  |  |  | 2020-02-03 | 2020-02-07 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-03 | 2020-02-07 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
118 | Conduct Acceptance Testing |  |  |  | 2020-02-07 | 2020-02-07 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-07 | 2020-02-07 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
119 | Migration Sign off | ü | û |  | 2020-02-10 |  | -31336 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-10 |  | -31336 | Actual | bar: 2019-08-26 to 2020-02-21
120 | Migration Group 19 |  |  |  | 2020-02-03 | 2020-02-17 |  | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-03 | 2020-02-17 |  | Actual | bar: 2019-08-26 to 2020-02-21
121 | Prepare Migration Group worksheet |  |  |  | 2020-02-03 | 2020-02-06 | 4 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-03 | 2020-02-06 | 4 | Actual | bar: 2019-08-26 to 2020-02-21
122 | Submit Workload Migration ticket |  |  |  | 2020-02-07 | 2020-02-07 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-07 | 2020-02-07 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
123 | Perform Cut over |  |  |  | 2020-02-10 | 2020-02-14 | 5 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-10 | 2020-02-14 | 5 | Actual | bar: 2019-08-26 to 2020-02-21
124 | Conduct Acceptance Testing |  |  |  | 2020-02-14 | 2020-02-14 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-14 | 2020-02-14 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
125 | Migration Sign off | ü | û |  | 2020-02-17 |  |  | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-17 |  |  | Actual | bar: 2019-08-26 to 2020-02-21
126 | Closeout |  |  |  | 2020-02-05 | 2020-02-21 |  | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-05 | 2020-02-02 |  | Actual | bar: 2019-08-26 to 2020-02-21
126 | Finalize documentation |  |  |  | 2020-02-05 | 2020-02-18 | 10 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-05 | 2020-02-18 | 10 | Actual | bar: 2019-08-26 to 2020-02-21
127 | Documentation Closure and review | ü |  |  | 2020-02-19 | 2019-09-09 | -118 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-19 | 2019-09-09 | -118 | Actual | bar: 2019-08-26 to 2020-02-21
128 | Documentation Sign off | ü |  |  | 2020-02-20 | 2020-02-20 | 1 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-20 | 2020-02-20 | 1 | Actual | bar: 2019-08-26 to 2020-02-21
129 | Engagement Review | ü |  |  | 2020-02-21 |  | -31345 | Planned | bar: 2019-08-26 to 2020-02-21
[5 empty] | 2020-02-21 |  | -31345 | Actual | bar: 2019-08-26 to 2020-02-21
[5 empty] | ü | Milestone |  |  | 2019-08-29: Planned; 2019-09-05: Actual / Projected
[5 empty] | û | Client Work

## Notes
ToDo: | Needs: |  | Status
|  | Azure Subscription access | Requested
|  | Service Principal (for Cloud Health) | Open
|  | Azure VDC Documentation | Open
|  | Nora / Ryan Jira access | Open | Send names
|  | Confluence Access for team | Open

## Travel Schedule
[15 empty] | Halloween | [7 empty] | Thanks Giving | [7 empty] | Chirstmas |  | New Years
| Monthly Onsite |  | 2019-09-16 |  | 2019-09-23 |  | 2019-09-30 |  | 2019-10-07 |  | 2019-10-14 |  | 2019-10-21 |  | 2019-10-28 |  | 2019-11-04 |  | 2019-11-11 |  | 2019-11-18 |  | 2019-11-25 |  | 2019-12-02 |  | 2019-12-09 |  | 2019-12-16 |  | 2019-12-23 |  | 2019-12-30 |  | 2020-01-06 |  | 2020-01-13 |  | 2020-01-20 |  | 2020-01-27
|  |  | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure | Arrival | Departure
John Perry | 2 |  |  |  | 2019-09-25 | 2019-09-25 |  |  |  |  | 2019-10-17 | 2019-10-17 |  |  | 2019-10-29 | 2019-10-30 |  |  | 2019-11-12 | 2019-11-13
Mark Hanson | 1 |  |  |  | 2019-09-25 | 2019-09-25
Ryan McClish | 1 |  |  |  | 2019-09-25 | 2019-09-26 |  |  |  |  | 2019-10-15 | 2019-10-17 | [6 empty] | 2019-11-12 | 2019-11-14 | [6 empty] | 2019-12-10 | 2019-12-12
Deldri Dugger | 4 | Tues/Thurs |  |  | 2019-09-25 | 2019-09-25 | 2019-10-01 | 2019-10-03 | 2019-10-08 | 2019-10-10 | 2019-10-15 | 2019-10-17 | 2019-10-22 | 2019-10-24 | 2019-10-29 | 2019-10-29 | 2019-11-05 | 2019-11-07 | 2019-11-12 | 2019-11-14 | 2019-11-19 | 2019-11-21
Russ Henderson | 0
Mason Adams | 0
Marshall Choate | 0
Angel Garcia | 0
Scott Hiss | 4 |  |  |  | 2019-09-25 | 2019-09-26 | 2019-09-30 | 2019-10-03 | 2019-10-07 | 2019-10-10 | 2019-10-14 | 2019-10-17 | 2019-10-21 | 2019-10-24 | 2019-10-28 | 2019-10-29 | 2019-11-04 | 2019-11-07 | 2019-11-11 | 2019-11-14 | 2019-11-18 | 2019-11-21
Legend
Formulas:
New Years = [Chirstmas]+7

## Holidays
Holiday | Date
New Years | 2019-01-01
Memorial Day | 2019-05-27
Independence Day | 2019-07-04
Labor Day | 2019-09-02
Thanksgiving | 2019-11-28
Thanksgiving | 2019-11-29
Christmas | 2019-12-25
New Years | 2020-01-01
Boat Party
MSFT Conference Day 1
MSFT Conference Day 2
MSFT Conference Day 3
1oth Company Meeting
Relativity Fest | 2019-10-21
Relativity Fest | 2019-10-22
Relativity Fest | 2019-10-23
* Besure to add in 10th day like boat event or MSFT conferences

## Planning
|  | September 2019 | [22 empty] | October 2019 | [13 empty] | November 2019 | [22 empty] | December 2019 | [11 empty] | January 2020 | [22 empty] | February 2020
Sprint 2 | [24 empty] | Sprint 3 | [10 empty] | Sprint 4 | [9 empty] | Sprint 5 | [9 empty] | Sprint 6 | [9 empty] | Sprint 7
|  | Week 0 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Closeout
|  | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
Kickoff Meeting | bar: Week 8 21 to Week 8 22; Week 14 1
VDC Remediation | bar: Week 1 30 to Week 4 25; Week 8 21 to Week 8 22; Week 14 1
Phase I | bar: Week 1 30 to Week 7 15; Week 8 21 to Week 8 22; Week 14 1
Migration Pilot | bar: Week 1 30 to Week 3 18; Week 8 21 to Week 8 22; Week 14 1
Migration Group 1 | bar: Week 4 21 to Week 5 1; Week 8 21 to Week 8 22; Week 14 1
Migration Group 2 | bar: Week 6 4 to Week 7 15; Week 8 21 to Week 8 22; Week 14 1
Phase 2 | bar: Week 8 18 to Week 9 26; Week 10 2 to Week 13 24; Week 13 26 to Week 14 3
Migration Group 3 | bar: Week 8 18 to Week 9 26; Week 10 2 to Week 10 3; Week 14 1
Migration Group 4 | bar: Week 8 21 to Week 8 22; Week 10 4 to Week 12 18; Week 14 1
Migration Group 5 | bar: Week 8 21 to Week 8 22; Week 12 19 to Week 13 24; Week 13 26 to Week 14 3
Phase 2 | bar: Week 8 18 to Week 9 26; Week 10 2 to Week 13 24; Week 13 26 to Week 13 27; Week 14 1
Migration Group 3 | bar: Week 8 18 to Week 9 26; Week 14 1
Migration Group 4 | bar: Week 8 21 to Week 8 22; Week 10 2 to Week 11 13; Week 14 1
Migration Group 5 | bar: Week 8 21 to Week 8 22; Week 12 16 to Week 13 24; Week 13 26 to Week 13 27; Week 14 1
Phase 3 | bar: Week 8 21 to Week 8 22; Week 14 1; Week 15 6 to Week 20 14
Migration Group 6 | bar: Week 8 21 to Week 8 22; Week 14 1; Week 15 6 to Week 16 17
Migration Group 7 | bar: Week 8 21 to Week 8 22; Week 14 1; Week 17 20 to Week 18 31
Migration Group 8 | bar: Week 8 21 to Week 8 22; Week 14 1; Week 19 3 to Week 20 14
Closeout | bar: Week 8 21 to Week 8 22; Week 14 1; Week 20 10 to Closeout 21
Disaster Recovery Documentation | bar: Week 8 21 to Week 8 22; Week 14 1
Final Readout | bar: Week 8 21 to Week 8 22; Week 14 1; Closeout 19
Migration group 1
Prepare Migration Group worksheet | 10M
Submit workload migration ticket | 10M
Perform workload migration | 10M
Conduct application Testing | Relativity
Workload migration acceptance | Relativity
Migration group 2
Prepare Migration group worksheet
Submit workload migration ticket
Perform workload migration
Conduct application Testing
Workload migration acceptance
Migration group 3
Prepare Migration group worksheet
Submit workload migration ticket
Perform workload migration
Conduct application Testing
Workload migration acceptance
Migration group 4
Prepare Migration group worksheet
Submit workload migration ticket
Perform workload migration
Conduct application Testing
Workload migration acceptance
Migration group 5
|  |  |  | t | Project Kickoff
Migration Group 1 (Pilot)
Migration Group 2
Migration Group 3
Migration Group 4
[22 empty] | Engagement |  |  |  | Migration / Hand-off
Server Inventory Validation
Replication Engine
Migration group 6 |  | Week 5 28: t; Week 5 29: List of servers and Product Owners in Group 5
Prepare Migration group worksheet |  | Week 5 1: t; Week 6 4: Custom Build server list, specs and prioritization
Submit workload migration ticket |  | Week 5 28: Group 5
Perform workload migration |  | Week 5 28: Engagement; Week 6 4: Discovery; Week 7 11: Migration / Hand-off
Workload migration acceptance |  | Week 6 4: t; Week 6 5: List of servers and Product Owners in Group 6
[36 empty] | t | All remaining Groups and Product Owners
Perform workload migration |  | Week 6 4: Group 7
Conduct application Testing |  | Week 6 4: Engagement; Week 7 11: Discovery; Week 8 18: Migration /Hand-off
Group 6
Workload migration acceptance |  | Week 6 4: Engagement; Week 7 11: Custom Discovery; Week 8 18: Relativity Custom Build & Application Installation; Week 10 2: Migration / Hand-off
[37 empty] | Engagement |  |  |  |  | Standard Discovery | [9 empty] | Std Migration / Hand-off
Migration group 8
Prepare Migration group worksheet |  | Week 8 18: Custom Build Servers
Workload migration acceptance
Workload migration acceptance |  | Week 7 11: Group 8
Migration group 10 |  | Week 7 11: Engagement; Week 8 18: Custom Discovery; Week 9 25: Relativity Custom Build & Application Installation; Week 11 9: Migration / Hand-off
[42 empty] | Engagement |  |  |  |  | Standard Discovery | [9 empty] | Std Migration / Hand-off
Prepare Migration group worksheet
Submit workload migration ticket |  | Week 9 25: Group 9
Perform workload migration |  | Week 9 25: Engagement; Week 10 2: Custom Discovery; Week 11 9: Relativity Application Installation; Week 12 16: Migration / Hand-off
[52 empty] | Engagement |  |  |  |  | Standard Discovery |  |  |  |  | Std Migration / Hand-off
Conduct application Testing
Workload migration acceptance |  | Week 11 9: Project Closure
[63 empty] | t | Document Review
[67 empty] | t | Project Closeout Meeting

## Milestones
Activity | Start Date | End Date | Status | Comments