## Risks, Issues, & Actions Log
Relativity Azure Enterprise Migration - Risks, Actions, Issues, & Decisions (RAID) Log
68 total items
[13 empty] | 0 late | 66 closed
ID | Work Stream | Team | Type | Category | Migration Group | Server Name(s) | Description | Mitigation | Date Raised | Raised By | Team Owner | Individual Owner | Due Date | Current State | Date Closed | Running Notes
1 | Infrastructure | Client | 1. Issue | Technical |  | N/A | Dynamics of server list causing delays in planning and contacting App Owners | Consolidate server inventory and validate with Relativity infrastructure team and lockdown servers as final scope | 2019-10-03 | Deldri Dugger | 10M | Deldri Dugger | 2019-11-01 | Closed |  | 10/7: Uploaded new master list to Teams 10/25: New list to be provided. 11/06: Received Group 6 and custom server builds
2 | Infrastructure | Client | 3. Action | Technical |  | N/A | Microsoft’s timing for a solution supporting the migration file shares greater than 100TB | Implications to migration effort as they have several fileshares which exceed that size | 2019-10-03 | Peter Johnson | 10M | John Perry | 2019-10-11 | Closed | 2019-10-16 | 10/3 DRD: Awaiting response from Microsoft 10/16 DRD: Microsoft does not have a solution for this on their roadmap. Inquired with Peter if he'd like to develop a use case and he declined
3 | Application | Client | 3. Action | Technical |  | N/A | OCR application utilizes SMTP to send a confirmation email upon successfule scanning. | Azure will require the use of a SMTP relay. Recommendation to the application team is needed for them to take action/make changes. Application team is functional as configured. | 2019-10-02 | Scott Hiss | 10M | John Perry | 2019-10-25 | Closed | 2019-10-18
4 | Infrastructure | Client | 2. Risk | Technical |  | N/A | Although the OCR team does not require it, the Worker servers include Invariant for use by the imaging process. This software may have port/firewall requirements and will need to be investigated. | Identify any special considersions/configurations required by the Invariant software and incorporate it into the migration setup. | 2019-10-02 | Scott Hiss | 10M | Scott Hiss | 2019-10-25 | Closed | 2019-10-18 | 10/17: Invariant servers should be moved as replicated as currently deployed. Guidelines are: 1-2 workers requires 16GB RAM, 4 Cores, 4Gps IO 3-7 workers requires 32GB RAM, 4-8 Cores, 4-8Gps IO 8+ workers requires 64GB RAM, 4-8 Cores, 408Gps IO
5 | Infrastructure | Client | 1. Issue | Technical | 5 | IL1DDCHMRXAP001 | IL1DDCHMRXAP001 - Replication will not start due to errors, check server logs | Repair, update, or reinstall the Hyper-V Guest Integration Services on the VM | 2019-10-31 | Russ Henderson | Client | Raji Kaur | 2019-11-04 | Closed |  | 11/11: Raji applied registry fix on host and failed over this weekend 11/06 SLH: Requested 10M assistance in identifying issue. Open MS ticket if the problem cannot be determined.
6 | Infrastructure | Client | 1. Issue | Technical | 5 | DV-W2R-009-W10 | OS disk size is greater than 300GB, which is not supported for Gen 2 VMs. |  | 2019-10-31 | Russ Henderson | Client | Cameron Peppers | 2019-11-08 | Closed |  | 11/20 DRD: Received update from owner: all VMs cannot connect to Proget/Artifactory - a 403 error is returned; and virtualization does not work 11/18: Raji: This VM has been migrated to Azure. Server owner is aware 11/15: Raji - server owner said this afternoon or the weekend is ok for us to work on the server. 11/12: Server owner is running a long job and we cannot shut down this server to reduce vhdx size until atleast Thursday the 14th. Will follow up then. 11/12: Cameron working with PO reduce the size 11/08 SLH: Workstation disk is under 200G. Hyper-v side to be shrunk and cutover to be scheduled for week of 11/11. 11/07: Drive to be shrunk tonight 11/06 SLH: Product owners cleaning up VMs. Then will replicate and perform cutover sometime 11/11-14
7 | Infrastructure | Client | 1. Issue | Technical | 5 | DV-W2R-109-W10 | OS disk size is greater than 300GB, which is not supported for Gen 2 VMs. |  | 2019-10-31 | Russ Henderson | Client | Cameron Peppers | 2019-11-08 | Closed |  | 11/20 DRD: Received update from owner: all VMs cannot connect to Proget/Artifactory - a 403 error is returned; and virtualization does not work 11/19: Raji: VM has been migrated; Server owner is aware 11/18: Raji: VM has been replicated but not cutover, was very slow replication. Server owner says ok to migrate after Noon Chicago time. Will plan to cutover later today. 11/15: Raji - server owner said this afternoon or the weekend is ok for us to work on the server 11/12: Server owner is running a long job and we cannot shut down this server to reduce vhdx size until atleast Thursday the 14th. Will follow up then. 11/12: Cameron working with PO reduce the size 11/11: Raji to check with Cameron
8 | Infrastructure | Client | 1. Issue | Technical | 3 | IL1DDML021DB001 IL1DDML021DB002 IL1DDML021DB003 | Replication failing due to errors | Repair, update, or reinstall the Hyper-V Guest Integration Services on the VM | 2019-10-25 | Russ Henderson | Client | Raji Kaur | 2019-11-01 | Closed |  | 11/11- Raji - replication and migration completed for ddml021db001/002/003 - owner has been notified. 11/11: Raji performed replication and migration for 2 of 3; looking for window to failover. Other still pending. 11/06 SLH: Check logs and correct condition. Work with Microsoft to resolve.
9 | Infrastructure | Client | 1. Issue | Technical |  | IL1DPBOARDWB001 | Primary or recovery machine no longer available | Descoped | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed |  | 11/07: Descoped per Raji Kaur during Stand-up 11/06 SLH: Defer migration/cutover to 11/11 or 11/12
10 | Infrastructure | Client | 1. Issue | Technical | 5 | IL1DPRAPGUID001 | Replication will not start due to errors, check server logs | Repair, update, or reinstall the Hyper-V Guest Integration Services on the VM | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed |  | 11/20 DRD: Scott spoke with Raji, several server are being moved to managed disk as part of a different effort. This server will be added to that list. 11/19 DRD: Need outage window to change to managed disk. 11/18 DRD: Unable to perform post-migation activities due to issue with Azure VM Agent 11/18: Owner will test today 11/15: Migration completed; 10x to reach out to owner to validate and get signoff 11/14: Replication done; Raji will migrate after hours today 11/13: Replication kicked off and by evening was at 70%. Once completed will plan to failover on 11/14 evening 11/12: Raji trying to move 11/11: John to check the sizing and determine approach for resolution 11/06 SLH: Defer migration/cutover to 11/11 or 11/12
11 | Infrastructure | Client | 1. Issue | Technical |  | IL1DPRAPGUID002 | Incorrect VNET mapping |  | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed | 2019-11-06 | 11/06 SLH: Defer migration/cutover to 11/11 or 11/12
12 | Infrastructure | Client | 1. Issue | Technical |  | IL1DDCHMRXAP001 | Replication will not start due to errors, check server logs | Repair, update, or reinstall the Hyper-V Guest Integration Services on the VM | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed | 2019-11-06 | 11/06 SLH: DUPLICATE
13 | Infrastructure | Client | 1. Issue | Technical | 5 | IL1IDCMARXWB001 | Unable to start replication - Server can't be found in any of the clouds, also looked for similar names and couldn't find anything. | Repair, update, or reinstall the Hyper-V Guest Integration Services on the VM | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed |  | 11/14 SLH: PO confirmed server is functional. 11/12: Scott to contact PO for validation and signoff 11/11 - Raji - system owner gave the green light for off hours cutover. Migration is complete. Need owner to validate and signoff during the next work day. 11/11/ - Raji- Replication is complete. Ready for cutover. Reach out to owner for window to do that. 11/11: John to check the sixing and determine approach for resolution 11/06 SLH: Requested 10M assistance in identifying issue. Open MS ticket if the problem cannot be determined.
14 | Infrastructure | Client | 1. Issue | Technical |  | IL1DPCHMRXAP001 | Incorrect VNET mapping |  | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed | 2019-11-06 | 11/06 DRD: Confirmed with CMC server replicated and healthy
15 | Infrastructure | Client | 1. Issue | Technical |  | IL1DPCHMRXAP002 | Incorrect VNET mapping |  | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed | 2019-11-06 | 11/06 DRD: Confirmed with CMC server replicated and healthy
16 | Infrastructure | Client | 1. Issue | Technical |  | IL1DPCHMRXDB001 | Incorrect VNET mapping |  | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed | 2019-11-06 | 11/06 DRD: Confirmed with CMC server replicated and healthy
17 | Infrastructure | Client | 1. Issue | Technical |  | IL1DPCHMRXWB001 | Incorrect VNET mapping |  | 2019-11-04 | Russ Henderson | Client | Raji Kaur | 2019-11-06 | Closed | 2019-11-06 | 11/06 DRD: Confirmed with CMC server replicated and healthy
18 | Infrastructure | Client | 1. Issue | Technical | 5 | IL1IDCMARXWB001 | This server is critical and not currently syncing do to an issue connecting to azure storage. | Reinstall the Hyper-v integration services on the server | 2019-11-07 | CMC | Client | Raji Kaur | 2019-11-08 | Closed |  | Duplicate
19 | Infrastructure | Client | 1. Issue | Technical | 5 | IL1DTRELATAP608 | Target network mapping | Remap | 2019-11-07 | CMC | Client | John Perry | 2019-12-09 | Closed |  | 12/18 DRD: Scheduled for migration on 12/19 12/17 DRD: Sent migration request to owner 12/13 RH: Need to schedule migration with owner 12/11 DRD: Ready for cutover. 12/10 RH: Replication started 12/10 RH: Could not migrate - server will not add as a physical machine to the config server. Still troubleshooting. 12/09 DRD: Requested migration today 12/06 DRD: Servers were rebooted 12/05 DRD: Contacted Owner to schedule reboot 11/11: Pending implementation of config server
20 | Infrastructure | Client | 1. Issue | Technical | 5 | IL1DTRELATAP609 | Target network mapping | Remap | 2019-11-07 | CMC | Client | John Perry | 2019-12-09 | Closed |  | 12/18 DRD: Scheduled for migration on 12/1912/17 DRD: Sent migration request to owner 12/12 DRD: Fix and fully replicatied. Schedule migration with Owner 12/10 RH: Could not install mobility agent - not enough free disk space or the destination isn't a fixed disk. 12/10 RH: Could not migrate - server will not add as a physical machine to the config server. Still troubleshooting. 12/09 DRD: Requested migration today 12/06 DRD: Servers were rebooted 12/05 DRD: Contacted Owner to schedule reboot 11/11: Pending implementation of config server
21 |  |  | 1. Issue |  | 5 | IL1DPRAPGUID003 | Not connecting to the log analytics work space | Need to have the Azure VM Agnet installed on server |  |  |  | Raji Kaur | 2019-11-19 | Closed | 2019-11-15 | 11/21 DRD: Owner to test 11/19 SLH: Followed up with Mark Cison for status update on testing. 11/18: Raji: Installed VM Agent 11/18 DRD: Scott notified Owner to perform testing 11/18: Raji: Done 11/15 DRD: Need to have the Azure VM Agnet installed on server 11/07 DRD: Posted on Slack - @Raji Migration is complete. This is blocking the machine from being connected to a Log Analytics worksp ace.
22 |  |  | 1. Issue |  | 3 | IL1DDML021AG001 IL1DDML021AG002 IL1DDML021DB001 IL1DDML021DB002 IL1DDML021DB003 IL1DDML021WB001 | Environment performance is slower than on-prem. | 11/12: CMC observation for ML021 is that only DB003 should have memory bumped. The web server could be upped just a bit but none of the servers maxed out. |  |  |  | John Perry | 2019-11-13 | Closed |  | 11/20 DRD: Received update that upgrade and functional testing went well 11/19 DRD: Increased server to 16 CPU and 64GB memory 11/19 DRD: CPU is maxed out during upgrade on agent and web 11/18 DRD: Anatolii has begun test; outcome pending 11/15 DRD: Anatolii has not had an opportunity to test; outcome pending 11/14 DRD: Anatolii will performing testing tonight. Will let us know the outcome 11/13 DRD: Spoke with Anatolii to understand the performance degradation being experienced. In the process of resizing impacted servers. 11/12 SLH: Additional feedback from product owner - "i started upgrade ml021 yesterday and looks like it is just stock on SQL servers memory and CPU is close to 100 % ml021002 100%-CPU agent probably just stop on that one during upgrade i just realized that SQL memory is 32 GB , I think we had 64 before" 11/12: Hold off on increasing RAM due to capacity issues; open ticket/request with Microsoft 11/11 SLH: CMC team turned on monitoring for the environment. Anatolii's team executed their long running verification.
23 |  |  | 1. Issue |  | 3 | IL1DDML026AG001 IL1DDML026AG002 IL1DDML026DB001 IL1DDML026WB001 | Environment performance is slower than on-prem. | 11/12: CMC recommendation is to up the ram on the ML026 for all of the servers. |  |  |  | John Perry | 2019-11-13 | Closed | 2019-11-14 | 11/14: Anatolii reported performance is good and we can close 11/13 DRD: Anatolii reported an improved performance thus far and will provide updates tomorrow on final outcome of testing 11/13 DRD: Spoke with Anatolii to understand the performance degradation being experienced. Resized and rebooted the impacted servers. Notified Anatolii to perform testing. Awaiting outcome of test. 11/12: Hold off on increasing RAM due to capacity issues; open ticket/request with Microsoft 11/11: SLH: CMC team turned on monitoring for the environment. Anatolii's team executed their long running verification.
24 |  |  | 1. Issue |  | 5 | IL1DTRELATDB001 | Missing E drive (storage); drive has SQL database. Environment is completely not functional without SQL Server. | Restored database | 2019-11-11 | Viktar Karpach | Client | Raji Kaur | 2019-11-12 | Closed | 2019-11-13 | 11/13 DRD: Drive was restored by Raji 11/12 DRD: Raji working with Viktar to restore drive
25 |  |  | 1. Issue |  | N/A | N/A | Limited capacity in Azure Region for Relativity additional servers | Work with Microsoft to increase capacity | 2019-11-12 | Casey Ford | Client | John Perry | 2019-11-15 | Closed |  | 11/19: DRD: Initial assessment is complete. There appears to be several servers not visible; will revalidate. If cannot find, will need assistance to ensure all servers are in assessment. 11/14 DRD: Pending assessment information from John Perry 11/13: Mircosoft 11/12: Casey to write ticket and Rob to conduct follow-up with Mircosoft
26 |  |  | 4. Decision |  | N/A | N/A | Performance testing should be able to evaluate/simulate end-user performance. If servers are moved to the Azure environment, things like network latency will be lost in testing exercises. Should/Can the performance testing environment be deployed elsewhere? |  |  |  |  | Rob Fischer | 2019-11-22 | Closed |  | 12/19 DRD: Casey has 2 physical machinces to simulate customer latency 11/14: Schedule meeting with Scott Parillo to discuss 11/13 SLH: Spoke with Scott Parillo regarding outstanding questions he had for the Azure migration. These servers are currently targeted for migration in Group 6.
27 |  |  | 4. Decision |  | N/A | N/A | The API testing team has the ability to spin up/down VMs for testing purposes. Will this be allowed in the Azure environment? Future testing would include the spin-up of legacy versions of Relativity for backward compatabiity testing of APIs. This would require the ability for the test team to perform this function, too. |  |  |  |  | Casey Ford | 2019-11-22 | In Progress |  | 12/19 DRD: Casey to follow-up with Scott Parillo 11/14: Schedule meeting with Scott Parillo to discuss 11/13 SLH: Spoke with Scott Parillo regarding outstanding questions he had for the Azure migration. These servers are currently targeted for migration in Group 6.
28 |  |  | 1. Issue |  | 4 | IL1DDML027DB001 | Server on the wrong subnet | Move to correct subnet | 2019-11-13 | John Perry | 10M | CMC | 2019-11-15 | Closed | 2019-11-14 | 11/14 DRD: Server moved and owner updated 11/14 DRD: Contact owner for outage window, informed CMC. 11/13 DRD: Reported server need to be moved
29 |  |  | 1. Issue |  | 4 | IL1DDML151IV002 | Server on the wrong subnet | Move to correct subnet | 2019-11-13 | John Perry | 10M | CMC | 2019-11-15 | Closed |  | 11/15 DRD: CMC completed moved to correct subnet 11/14 DRD: Contact owner for outage window; awaiting response. 11/13 DRD: Reported server need to be moved
30 |  |  | 1. Issue |  | 7 | IL1CCRCAINAG963 IL1CCRCAINAG964 IL1CCRCAINAN962 IL1CCRCAINDB962 IL1CCRCAINIV962 IL1CCRCAINWB962 IL1CCRCAINWK962 IL1CCRCAINDG961 IL1CCRCAINWK963 IL1CCRCAINAG965 IL1CCRCAINAG966 IL1CCRCAEXAG961 IL1CCRCAEXDB961 IL1CCRCAEXAN961 IL1CCRCAEXIV961 IL1CCRCAEXDG961 IL1CCRCAEXWB961 IL1CCRCAEXWK961 IL1CCRCAEXAG962 IL1CCRCAEXWK962 IL1CCRCAEXAG963 IL1CCRCAEXAG964 | site recovery does not see the server | validate the tool has access to the servers | 2019-11-14 | John Perry | Client |  | 2019-11-15 | Closed |  | 11/14 DRD: Servers removed from scope per Charlie Saxe
31 |  |  | 1. Issue |  | 7 | IL1IPLICMNGR001 | site recovery does not see the server | validate the tool has access to the servers | 2019-11-14 | John Perry | Client | Raji Kaur | 2019-11-18 | Closed | 2019-11-15 | 11/15 DRD: CMC reported server have completed replication successully 11/14: Raji - don't know what the issue is, this is being replicated 11/14 DRD: Reported replication issue
32 |  |  | 1. Issue |  | 7 | IL1CCRCAONDB971 | This has an issue connecting to Azure storage and hasn't replicated yet. Its in the 11/20 cutover. | Move these servers to the hyper-v host that has the registry key that microsoft told her to add. |  |  |  | John Perry | 2019-11-19 | Closed |  | 11/21 DRD: Server cutover and Owner performed testing 11/20 DRD: Move to the correct host but still not replacating; need access to logs to research root cause 11/19 DRD: Experiencing issue: VMM/ Azure Site Recovery service could not find a Hyper-V host. Not able to replicate yet. 11/19 DRD: Received error during replication and reported to Raji
33 |  |  | 1. Issue |  | 7 | IL1CPSAPOCDB001 | il1cpsapocdb001 This has an issue connecting to Azure storage and hasn't replicated yet. Its in the 11/21 cutover. | Move these servers to the hyper-v host that has the registry key that microsoft told her to add. |  |  |  | Raji Kaur | 2019-11-20 | Closed |  | 11/19 DRD: Replicated and in a healthy state 11/19 DRD: Received error during replication and reported to Raji
34 |  |  | 1. Issue |  | 7 | IL1CPSAPOCWK001 | This has an issue connecting to Azure storage and hasn't replicated yet. Its in the 11/21 cutover. | Move these servers to the hyper-v host that has the registry key that microsoft told her to add. |  |  |  | Raji Kaur | 2019-11-20 | Closed |  | 11/19 DRD: Replicated and in a healthy state 11/19 DRD: Experiencing issue: VMM/ Azure Site Recovery service could not find a Hyper-V host. 11/19 DRD: Replicated and in a healthy state 11/19 DRD: Received error during replication and reported to Raji
35 |  |  | 1. Issue |  | 7 | Sales POC | Mapped to the RCA_Prep Resource Group and network in error | Submit change request for build of new subnets and create new Resource Group | 2019-11-21 | CMC | 10M | CMC | 2019-12-06 | Closed |  | 12/09 DRD: Confirmed move to new Resource Group on 12/11 12/05 DRD: Scheduled to be moved to new Resource Group/Subnet on Dec 11 per Jerry'a approval 12/04 DRD: CR Approved 12/02 DRD: Russ provided information to Raji for Change Request 11/26 DRD: John drafting subnet information for the Change Control 11/22 DRD: Jerry Grace onboard with approach 11/21 DRD: Need to discuss with Relativity leadership and select an option for path forward
36 |  |  | 1. Issue |  | 6 | IL1CCRCAINDT971 IL1CCRCAINDB971 IL1CCRCAEXAG971 IL1CCRCAEXAG972 IL1CCRCAEXAN971 IL1CCRCAEXDB971 IL1CCRCAONAG971 IL1CCRCAONAG972 IL1CCRCAONAN971 IL1CCRCAONCO971 IL1CCRCAONDB971 IL1CCRCAONDT971 IL1CCRCAONDT972 IL1CCRCAONIN971 IL1CCRCAONSB971 IL1CCRCAONWB971 IL1CCRCAONWB972 IL1CCRCAONWK971 IL1CCRCAONWK972 | VM Agent Missing | Install agent | 2019-11-22 | CMC | 10M | CMC | 2019-11-22 | Closed |  | 11/27 DRD: Peter installed agent. 11/26 DRD: John Perry to work with Peter Johnson to get Agnet installed on servers. 11/22 DRD: Reached out to Raji to propose that Relativity provide 10M with access so that we can install the agent moving forward
37 |  |  | 3. Action |  | 7 | IL1IPLICMNGR001 | License Manager - critical - will be done by Raji |  |  |  |  | Raji Kaur |  | Closed |  | 11/26 DRD: Server remiaining from Group 7 still needs to migrated to Azure
38 |  |  | 1. Issue |  | 6 | IL1DDFJAWSAP001 IL1DDPRCDBIV001 IL1DDPRCDBWK001 IL1DDPRCDBWK002 IL1DDPRCRBIV001 IL1DDPRCRBWB001 IL1DDPRCRBWK001 IL1DTFJAWSAP001 | site recovery does not see the server. |  |  |  |  | Cameron Peppers | 2019-11-27 | Closed |  | 11/27 DRD: Cameron added servers to Azure 11/26 DRD: Email Charlie and Cameron regrading issue
39 |  |  | 1. Issue |  | 6 | BLD-PKGS | Disk size not supported |  |  |  |  | Russ Henderson | 2019-12-09 | Closed |  | 12/17 DRD: Descope per Casey; IT Ops will handle post migration 12/16 DRD: Still trying to reduce the disk size 12/12 DRD: IT was able to shrink the disk under 8 TB but need to shrink Hyper-v side which requires downtime 12/11 DRD: Contact Tools about what can be done; sensitive server 12/09 DRD: Cannot be migrated via ASR; will follow-up with Raji on alternatives 12/06 RH: Disk size is too large for ASR config server replication. Data from Azure Migrate was misleading. Verified from VMM the server has a disk larger than 8TB, which is not supported with ASR. 12/03 DRD: Move to migration group 8 (next week) 12/02 DRD: Will attempt to use the configuration server to migrate the server 11/27 DRD: Due to size the server will need to be migrated using the Config server 11/27 DRD: Notified Peter of issue
40 |  |  | 1. Issue |  | 6 | IL1DPTSTCMDB001 | Hyper V |  |  |  |  | Peter Johnson | 2019-11-27 | Closed |  | 11/27 DRD: Notified Peter of issue
41 |  |  | 1. Issue |  | 6 | IL1DTMLRMTAG001 IL1DTMLRMTAN001 IL1DTMLRMTDB001 IL1DTMLRMTDB002 IL1DTMLRMTFS001 IL1DTMLRMTIV001 IL1DTMLRMTSB001 IL1DTMLRMTSB002 IL1DTMLRMTWB001 IL1DTMLRMTWB002 IL1DTMLRMTWB003 IL1DTMLRMTWK001 IL1DTOUTINFS001 IL1DTRMTCHEF001 IL1DDFTAASFS001 IL1DDINVWRK001 IL1DDINVWRK002 IL1DDTAPIRAP001 | site recovery does not see the server. |  |  |  |  | Cameron Peppers | 2019-12-02 | Closed |  | 11/27 DRD: Sent email to Charlie, Cameron and Peter regarding issue
42 |  |  | 1. Issue |  | 8 | il1ddcllctcl001 IL1IPRFLCTDB005 IL1IPRFLCTDB007 IL1IPRSADAP001 IL1IPSCCMWU001 IL1IPSCORCAP001 IL1IPSFXDATA001 IL1IPTIMESWB002 IL1IPWSUSMG001 IT-CERTSUB01 IT-OKTA03 IT-SCCM IT-SRV-JTBRN2 PROD-DIRSYNC01 prod-exhyb01 PROD-EXHYB02 r1-mid-01 R1-MID-02 util-wsus01 | Not visible in VMM |  |  |  |  | Cameron Peppers | 2019-12-05 | Closed |  | 12/04 RH: All have been added to the DR-ASR cloud. 12/03 DRD: Still blocked or having replication issues 12/01 DRD: Sent email to Clarlie and Cameron
43 |  |  | 1. Issue |  | 6 | IL1DTOUTINFS001 | Disk size not supported |  |  |  |  | Russ Henderson | 2019-12-11 | Closed |  | 12/17 DRD: Scheduled for Dec 18th 12/17 RH: Replicated and in sync, need to schedule migration with the owner ASAP 12/12 DRD: Replaction failed; need to engage Microsoft 12/10 RH: Replication started 12/10 RH: Replication issues, troubleshoting 12/09 DRD: Schedule to migrate on 12/12 12/05 DRD: Contacted Owner to schedule reboot 12/2 RH: Use configuration server
44 |  |  | 1. Issue |  | 6 | IL1DDINVWRK001 | Replication will not start due to errors, check server logs |  |  |  |  | Russ Henderson | 2019-12-09 | Closed |  | 12/17 DRD: Scheduled for Dec 18th per owner 12/17 RH: Ready to migrate, needs to be scheduled with the owner 12/16 DRD: Needs to be rebooted for replication 12/13 RH: Server is down on prem - need to boot and replicate to get in sync. Need to schedule failover when in sync. 12/10 DRD: Owner granted permission for 12/10 @ 12 noon; reboot completed at 12:12 pm by Raji 12/09 DRD: Contact Owner for disable Secure Boot 12/4 RH: Possibly could use configuration server.
45 |  |  | 1. Issue |  | 6 | IL1DDINVWRK002 | Not found in a cloud |  |  |  |  | CMC |  | Closed |  | 12/4 RH: Raji added to cloud, replication started.
46 |  |  | 1. Issue |  | 6 | IL1DDTAPIRAP001 | OS disk size not supported |  |  |  |  | Russ Henderson | 2019-12-11 | Closed |  | 12/09 DRD: Scheduled for 12/12 12/05 DRD: Contacted Owner to schedule reboot 12/2 RH: Use configuration server
47 |  |  | 1. Issue |  | 6 | IL1DPTSTCMDB001 | Replication will not start due to errors, check server logs |  |  |  |  | Russ henderson | 2019-12-09 | Closed |  | 12/09: Scheduled for 12/11 12/05 DRD: Contacted Owner to schedule reboot 12/04 DRD: Need SecureBoot disabled before replication 12/4 RH: Possibly could use configuration server.
48 |  |  | 1. Issue |  | 6 | KIE-APP-MON-01 | Replication will not start due to errors, check server logs |  |  |  |  | CMC | 2019-12-09 | Closed |  | 12/10 DRD: Replication started 12/09 DRD: Replication failure 12/05 DRD: Schedule to be migrated on Dec 11 with Jerry's other servers. Coordinate DNS change for 6 pm. Resource group KIE-RG 12/4 RH: Found in cloud, but could not start replication due to errors. Would like to attempt replication with the configuration server.
49 |  |  | 3. Action |  | N/A | N/A | Open support ticket for Registry Key issue |  |  |  |  | Russ Henderson | 2019-12-06 | In Progress |  | 12/16 DRD: Pending more details from MS 12/12 DRD: Microsoft reported ... 12/09 DRD: Ticket submitted to Microsoft
50 |  |  |  |  | 8 | IL1DDTAPIASPERA002 | Could not install mobility agent - not enough free disk space or the destination isn't a fixed disk. |  |  |  |  | Raji Kaur |  | Closed |  | 12/12 DRD: Completed and failed over today
51 |  |  |  |  | 8 | IL1DTIMPEXWB001 | Secure boot enabled |  |  |  |  | Russ Henderson |  | Closed |  | 12/11 RH: Disabled secure boot
52 |  |  |  |  | 8 | IL1IPPLYCMFT001 | Secure boot enabled |  |  |  |  | Russ Henderson |  | Closed |  | 12/11 RH: Disabled secure boot
53 |  |  |  |  | 8 | PM-ARTICULATE02 | Enable protection failed error code EP0867. The server 172.18.1.22 is already protected with a different Configuration server. |  |  |  |  | Russ Henderson |  | Closed |  | 12/12 DRD: Issue addxressed . Restarting replication
54 |  |  | 1. Issue |  | 8 | IL1DTIMG94AP001 | Need to add to a different cloud. In Regression cloud which is not available in ASR. |  |  |  |  | Raji Kaur |  | Closed |  | 12/12 DRD: Server has been moved to cloud; replication in process
55 |  |  | 1. Issue |  | 8 | BLD-MSTR-01 | Determine migration date |  |  |  |  | Casey Ford | 2019-12-17 | Closed |  | 12/17 DRD: Descope per Casey; need window to migrate - IT Ops will handle post migration 12/13 DRD: Received email that they want to post until next year; Casey to follow 12/12 DRD: Replication in process
56 |  |  | 1. Issue |  | 8 | il1dppypisap001 | Determine migration date |  |  |  |  | Casey Ford | 2019-12-17 | Closed |  | 12/17 DRD: Descope per Casey; need window to migrate - IT Ops will handle post migration12/13 DRD: Working with owners to identify dates for migration
57 |  |  | 1. Issue |  | 8 | IL1DPFPKGSFS001 | Determine migration date |  |  |  |  | Casey Ford | 2019-12-17 | Closed |  | 12/17 DRD: Descope per Casey; need window to migrate - IT Ops will handle post migration 12/13 DRD: Working with owners to identify dates for migration
58 |  |  | 1. Issue |  | 8 | DV-CHEFMGMT-01 | Determine migration date |  |  |  |  | Casey Ford | 2019-12-17 | Closed |  | 12/17 DRD: Descope per Casey; need window to migrate - IT Ops will handle post migration 12/13 DRD: Working with owners to identify dates for migration
59 |  |  | 1. Issue |  | TBD | il1ipsecursc001 il1ipsecursc002 | Unsupported version of Linux |  |  |  |  | John Perry | 2019-12-17 | Closed |  | 12/17 DRD: Casey requested 10M spin-up 2 Cali Linuz servers and let CJ import the data 12/17 RH: According to Cameron, this is an appliance and we do not have root access. This will prevent migration as the Azure VM agent cannot be installed. Same with SC002. This server cannot be migrated as it sit on an unsupported version of Linux Owner (CJ) wants IT Ops to try import/export
60 |  |  | 1. Issue |  | TBD | IL1DPBOMGRAP001 | Server is an appliance and cannot be migrated |  |  |  |  | Casey Ford | 2019-12-17 | Closed |  | 12/17 DRD: Descope per Casey; IT Ops will handle post migration IT Ops to build a new appliance in Azure or descope
61 |  |  | 3. Action |  | 8 | IL1DPCHEFHV001 IL1DPCHEFHV002 IL1DPCHEFHV003 IL1DPCHEFHV004 | Having issues with being able to ping from the inside the vm. This is breaking our builds of TestVM |  |  |  |  | TBD |  | Closed |  | 12/19 DRD: Fail forward; IT Ops will manage rollback if needed 12/17 DRD: Contact owner for root cause of issue; schedule meeting
62 |  |  |  |  | TBD | IL1IPLICMNGR001 | License Manager - determine migration date |  |  |  |  | Casey Ford |  | Closed |  | Descoped from 10M per Raji
63 |  |  |  |  | TBD | prod-rlt-lic | License Manager - determine migration date |  |  |  |  | Casey Ford |  | Closed |  | Descoped from 10M per Raji
64 |  |  | 1. Issue |  | 8 and 9 | PROD-DIRSYNC01 PROD-EXHYB01 PROD-EXHYB02 IL1DTDOCTSWB001 IL1DDPFPRCDG003 IL1IPTSANIAP001 IL1DTIMG94AP001 IL1IPSFXDATA001 IL1DPRAPGUID003 | Azure VM agent needs to be installed or reinstalled. |  |  |  |  | Raji Kaur |  | Closed |  | 12/19 DRD: Agent install and space complete 12/17 DRD: PROD-EXHYB01/02 Server were okay; did not rollback 12/16 DRD: Posted in Slack; completed by Raji Agent installed on all except IL1DTIMG94AP001 (out of space)
65 |  |  | 1. Issue |  | 9 | IL1DDPFPRCAG001 | Secure boot enabled |  |  |  |  | Russ Henderson |  | Closed |  | 12/17 RH: Was already being replicated via VMM, ready for cutover. Will proceed as normally.
66 |  |  | 1. Issue |  | 9 | IL1DDFTASMFS001 IL1DDFTASMFS002 IL1DDFTASMFS003 | Need root credentials enabled and added to the ASR configuration server account list to install the mobility agent |  |  |  |  | TBD |  | Closed |  | 12/18 RH: These are CentOS 7.7, which is not supported by ASR yet. Only up to CentOS 7.6 is supported for ASR. 12/17 DRD: Dana can enable root access to SAMBA - enablement completed for IL1DDFTASMFS001/ 002 / 003
67 |  |  | 1. Issue |  |  | IL1DDRELATWB001 | Not able to find this server or start replication. |  |  |  |  | Raji Kaur |  | Closed |  | 12/17 DRD: Descope per Casey 12/17 DRD: Raji to research
68 |  |  | 1. Issue |  |  | il1ipsecursc002 | This was migrated but will need to be rolled back as the Azure VM agent cannot be installed. |  |  |  |  | Russ Henderson |  | Closed |  | 12/17 DRD: Russ work with CJ to rollback

## Setup
Type List | Category List | Status | Yes No | Team | Priority | Work Stream
1. Issue | Business | New | Yes | Client | 1. Critical | Infrastructure
2. Risk | Technical | Assigned | No | 10M | 2. High | Application
3. Action | Project | In Progress |  | Microsoft | 3. Medium | Management
4. Decision | Client Organization | Closed |  | 3rd Party | 4. Low
5. Question | Operations | On Hold |  |  | 5. N/A
External
Application Team
Cloud Team