## Communication Plan
Migration Project Communication Plan
Name | Lead / Author | Project Phase | Audience | Purpose | Frequency | Method / Format | Duration | Notes | To-Do
Delivery Introduction to Client | BDM | Project Conception | Client Project Sponsor(s) Client Project Manager 10M CP/DD/DM 10M BDM & CSA |  | One time Post Win Notice | Meeting | 1 hr | To be scheduled by BDM To include 10M Delivery Management lead
Internal Demand to Delivery Transition | DD/DM | Project Conception | 10M CP/DD/DM 10M BDM & CSA 10M Tech Lead 10M Engineer(s) 10M Principal Architect(s) |  | One Time Post Client Intro Mtg | Meeting | 1 hr | to be scheduled by DD/DM to include staffed and supporting 10M team
Migration Welcome Kit | DD/DM | Project Conception | Client Project Sponsor(s) Client Project Manager 10M CP/DD/DM 10M BDM & CSA |  | One Time Post Client Intro Mtg | Email | N/A | to be sent by the DD/DM after the initial introduction with the client. Migration specific Welcome Kit to be sent with all pre-req's, documentation, process overview, milestone targets, etc.
Migration Process Review | DD/DM | Project Conception | 10M CP/DD/DM 10M Tech Lead 10M Migration Lead | Review the Migration Process, Cadence, Ingestion processes, etc associated with the engagement to prep the Client Project Manager with the approach for the engagement prior to going onsite | One time Post Welcome kit Post Staffing | Meeting | 1 hr | to be sent by the DD/DM after the welcome kit has been sent and the team has been staffed (Tech Lead)
Tooling Setup | DD/DM | Internal Mobilization | Client Engineer 10M Tech Lead 10M Migration Lead | Tooling Setup meetings to support client and the implementation of pre-req tools prior to onsite. | 2-3 meetings post welcome kit and post process review | Meeting(s) | 30-1 hr each | to be sent by the DD/DM after the welcome kit has been in the hands of the client and reviewed. Best to perform after the proces review meeting as well. Goal is to expedite and support the client to get our pre-req tools installed, setup, and get us access so we can see the data
Internal Migration Center Call | DD/DM | Internal Mobilization | 10M DD/DM 10M Tech Lead 10M Migration Lead 10M Migration Engineer(s) | Internal Migration Center and project team coordination and planning | weekly (1x / week) | Meeting | 30min | to be coordinated with the Migration Center Lead and scheduled by the DD/DM. goal is to maintain alignment, scheduling, and outstanding items for the Mgiration Center on a week by week basis to properly plan for upcoming weeks activities
Onsite Agenda and Mtg placeholder | DD/DM | Internal Mobilization | Full Client and 10M Team | Onsite Kickoff + Migration Planning Workshop | One Time | Meeting / Onsite | Full Day ( 6-8 hrs)
Project Kickoff - External Team | Delivery Director |  | Project Sponsor(s) Business Owner(s) SMEs Other Client Leads Project Manager | * Share Project Objective, Scope, project's success factors * Roles and responsibilities * Share other information such as what details will be communicated and how * Share timeline if applicable | Project Initiation | Meeting
Project Kickoff - Internal Team | Delivery Director |  | Project Team | * Set expectations and ground rules with the team (Logistics, team norms, dos & don'ts) * Level set the team to the project's success factors * Review roles and responsibilities | Project Initiation | Meeting
Daily Standup | Delivery Manager |  | Project Team | * Focus on progress on previous day, planned for the day and issues/obstacles from completing tasks. * Leave the standup with owners for issues, don't try to solve the issues during the standup. | Daily | Standup Meeting | 15-30min
CMC - Project Team Update (if CMC Project) | 10M CMC Lead |  | Project Team 10M Migration Lead 10M Migration Engineer(s) | * Review and schedule/plan upcoming activities / backlog review * Present and discuss blockers and resolution / RAID review * Discuss resource capacity and PTO | Weekly | Meeting | 30min
Team Project Status | Delivery Manager |  | Project Manager Leads | * Obtain a detailed update from the lead from each subteam to prepare for weekly project status. * Review risks and issues to determine which to address in project status | Weekly | Meeting
Executive Project Status | Delivery Manager |  | Project Sponsor(s) Business Owner(s) Project Manager | * Review Progress to plan * Review open issues & risks * Review open change requests * Identify decision makers / owners for action items. | Weekly | Meeting
Change Request Review | Delivery Manager |  | Project Sponsor Business Owner | * Review open and new Change Requests | As Needed | Meeting
Decisions / Changes | Delivery Manager / Leads |  | All | * When decisions are made (especially those that are different from the original assumptions), follow-up with an email explaining the situation, decision and impact if any. | As Needed | Email
Steering Committee | Delivery Director |  | Project Sponsor(s) Business Owner(s) | * Review overall project health with project stakeholders | Monthly | Meeting
Executive Sponsorship | Delivery Director |  | Executive Sponsor(s) (CTO, CIO, VP of Tech) | * Ensure that the project continualy supports the goals and startegy of the client | Monthly | Meeting
Knowledge Transfer | Technical Lead(s) |  | Technical Team | * Review the solution and technical implementation. This is to bridge the gap between the team that executed and the team that will own /manage the system moving forward | After milestones | Meeting
Project Closure | Delivery Manager |  | Project Sponsor(s) Business Owner(s) SMEs Other Client Leads Project Manager | * Review the delivered solution and high-level accomplishments of the project. Final sign off and approval of the project. | Post Project Delivery | Meeting