## RAID Log
Azure Migration - RAID Log
[10 empty] | 0 late | 1 closed
ID | Work Stream | Team | Type | Category | Migration Group | Description | Mitigation | Date Raised | Owner | Due Date | Current State | Close Date | Running Notes
1 | Infrastructure | Client | 1. Issue | Technical |  | Dynamics of server list causing delays in planning and contacting App Owners | Consolidate server inventory and validate with Relativity infrastructure team and lockdown servers as final scope | 2019-10-03 | Deldri Dugger | 2019-11-01 | Closed |  | 10/7: Uploaded new master list to Teams 10/25: New list to be provided. 11/06: Received Group 6 and custom server builds

## Setup
Type List | Category List | Status | Yes No | Team | Priority | Work Stream
1. Issue | Business | New | Yes | Client | 1. Critical | Infrastructure
2. Risk | Technical | Assigned | No | 10M | 2. High | Application
3. Action | Project | In Progress |  | Microsoft | 3. Medium | Management
4. Decision | Client Organization | Closed |  | 3rd Party | 4. Low
5. Question | Operations | On Hold |  |  | 5. N/A
External
Application Team
Cloud Team