## Sample Framework
Here is what each column represents at the project level:
ID | Title of Epic Root | Title of Major Phases that are children to the Epic | Titles of User Stories that are children of major phases | Titles of individual assigned tasks that are children of user stories | Description of the work item | Work Item Type | State | Reason | Assigned To
Do not copy the headers, they should alredy match before you copy the data. Copy below this line when creating a project.
| 10M-CustomerName |  |  |  | Root for Major Customer | Epic | New | New
|  | Onboarding |  |  | Onboarding and setup stuff | User Story | New | New
|  | Workload Discovery and Design |  |  |  | Feature | New | New
|  |  | WDD User Story1 |  |  | User Story | New | New
|  |  | WDD User Story2 |  |  | User Story | New | New
|  | VDC Deployment |  |  |  | Feature | New | New
|  |  | Security |  |  | User Story | New | New
|  |  |  | Create KeyVault Template |  | Task | New | New
|  |  |  | Security Center Policy configuration |  | Task | New | New
|  |  |  | Security Center Setup |  | Task | New | New
|  |  | Documentation |  |  | User Story | New | New
|  |  |  | Create Presentation |  | Task | New | New
|  |  |  | Create Visio Diagrams |  | Task | New | New
|  |  |  | Create Into/Solution Brief for POC VDC |  | Task | New | New
|  |  | Governance |  |  | User Story | New | New
|  |  |  | Create onboarding process |  | Task | New | New
|  |  |  | Create naming document |  | Task | New | New
|  |  |  | Create template to lock resources |  | Task | New | New
|  |  |  | Create subscription level policies |  | Task | New | New
|  |  | Network |  |  | User Story | New | New
|  |  |  | Create peering template |  | Task | New | New
|  |  |  | Create management network |  | Task | New | New
|  |  |  | Remove PIPs from current VDC |  | Task | New | New
|  |  |  | Create ASG templates |  | Task | New | New
|  |  | Workloads |  |  | User Story | New | New
|  |  |  | Configure automated patch management |  | Task | New | New
|  |  |  | Create Saturn deployment template |  | Task | New | New
|  |  |  | Create backup policy |  | Task | New | New
|  |  |  | Create recovery vault template |  | Task | New | New
|  |  |  | Add Azure Diagnostics Extensions |  | Task | New | New
|  |  |  | Add Animalware Extentions |  | Task | New | New
|  |  |  | Add OMS extensions |  | Task | New | New
|  |  |  | Create base VM templates |  | Task | New | New
|  |  | Audit |  |  | User Story | New | New
|  |  |  | Create SQL related dashboard |  | Task | New | New
|  |  |  | Create OMS audit dashboard |  | Task | New | New
|  |  |  | Collect all audit logs |  | Task | New | New
|  |  | IDP |  |  | User Story | New | New
|  |  |  | Install AAD Connect |  | Task | New | New
|  |  |  | Setup sync and configure passthrough auth |  | Task | New | New
|  |  |  | Create test/demo accounts in AAD & ADDS |  | Task | New | New
|  |  | Monitoring |  |  | User Story | New | New
|  |  |  | Create sample dashboard |  | Task | New | New
|  |  |  | Create backup dashboard |  | Task | New | New
|  |  |  | Create policy/procedure to monitor vm workloads |  | Task | New | New
|  | Migration |  |  |  | Feature | New | New
|  |  | Tooling Setup |  |  | User Story | New | New
|  |  |  | Setup ASR Components |  | Task | New | New
|  |  | Workload Setup |  |  | User Story | New | New
|  |  |  | Create Replication Groups |  | Task | New | New
|  |  |  | Replicate Group1 |  | Task | New | New
|  |  |  | Replicate Group2 |  | Task | New | New
|  |  | Migration |  |  | User Story | New | New
|  |  |  | Create Migration Groups |  | Task | New | New
|  |  | Cutover |  |  | User Story | New | New
|  |  |  | Create Cutover Groups |  | Task | New | New
|  |  |  | Compile coverrunbooks |  | Task | New | New
|  |  |  | Cutover Group1 |  | Task | New | New
|  |  |  | Cutover Group2 |  | Task | New | New
|  | Closeout |  |  |  | User Story | New | New