## Slide 1
Program & Planning
2020
2022
Migration Program Team
Migration Program Team
Migration Delivery Team A
Phase 1
Initial Success, Process Maturity, & Migration Team Scale
Phase 2 Business Unit aligned champions and migration teams, Special App Migration Teams, & initial EMR use cases
Project Start
Migration Resource Timeline
Phase 3 Remaining General Workloads,
EMR Migration and implementations
2021
Migration Delivery Team B
Migration Delivery Team C
Phase 0
Partnership, Commercials, Initial 2020 Migration Scope and Plan
Migration Delivery Team - Business Unit A
Migration Delivery Team - Business Unit B
Migration Delivery Team - Business Unit C
Migration Delivery Team - Business Unit n…
Migration Delivery Team - Critical App(s)
EMR Migration & Provisioning Team
100
EMR Migration & Provisioning Team
Migration Delivery Team A
Migration Delivery Team - Critical App(s)
Migration Support and Managed Services
Migration Delivery Team B
Migration Delivery Team n…
~2500
~9000
~15,000
Total Migrated Server estimate
Phase 2 kickoff
Phase 2 planning
Phase 3 planning
Phase 3 kickoff

## Slide 2
Migration Delivery Teams
Migration Support and Managed Services
Migration Program Team
Migration Team Roles
Role | Description | Resources
Program Manager | Overall Migration Program Leader responsible for planning, reporting, and communication to all stakeholders | 1 FTE
Lead Architect | Technical Architect and Migration Technical Leader to align process, support business and program level strategy, and decision making | 1 FTE
Role | Description | Resources
Cloud Migration Engineer(s) | Migration Center Engineering resources to support migration execution | 1 FTE / team
Delivery Manager | Workload and Team level scheduling, communication, and coordination | 1 FTE / team
Technical Business Analyst | Application and Workload Discovery, dependency mapping, and migration ingestion data collection | 1 FTE / team
Migration Architect | Tactical Migration Escalation and workload architecture decisions | 1 FTE / 3 teams
Role | Description | Resources
Migration Support Engineer(s) | Post-cutover support, troubleshooting, triage, follow-up, and operational support | Based on Azure Consumption; Month to Month