## Project Info
Client Name | Sample Client
Project Name | Enterprise Cloud Transformation
Project Start Date | 2020-03-09
Project Manager | Sample Managers Name
Assumptions Log tab:
Assumption Category
Business Requirements
Infrastructure
Resources
Architecture
Design
Other
Risk Log tab:
Escalation Level | Mitigation Strategy | Risk Status
1: Critical | Acceptance | Closed
2: High | Avoidance | Deferred
3: Medium | Preventative | On-going
4: Low
Issues Log tab: | Issue Priority
Issue Status | 4: Severe
Open | 3: High
Assigned | 2: Medium
Deferred | 1: Low
Resolved
Closed-No Action Required
Team Roster tab:
Active
Inactive
Pending

## Contact Info
Description | Internal/External | ROLE | EMAIL | Mobile Number
Security |  | CISO
Operations
Architecture
Operations |  | Infrastructure
Automation
Server
Identity AAD / AD
Storage
Backup
Database
BI
Networking |  | Network
Network
Engineering |  | Cloud Engineering and Governance
Cloud Engineering and Governance
DevOps |  | Cloud Engineering and Governance
Cloud Engineering and Governance
EA Application
Client Project Manager |  | 10m RM
Cloud Core Workstreams
Server Migration
Senior Server Engineer
Misc |  | EA
EA, Infrastructure, Security
Server
Security Architect
Manager of Server and Network teams
Senior Network Engineer

## Risk Log
Project: |  | Sample Client - Enterprise Cloud Transformation
Project Manager: |  | Sample Managers Name
# | Risk Description | Consequence/Impact | Escalation Level | Likelihood (%) | Mitigation Strategy | Mitigation Plan | Date Submitted | Assigned To | Target Date | Risk Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Project Planner
Sample Client - Enterprise Cloud Transformation | [63 empty] | Memorial Day
ID | ACTIVITY | Milestone | Client Work | D | START | END | DUR. |  | 2020-03-09 |  |  |  |  | 2020-03-16 |  |  |  |  | 2020-03-23 |  |  |  |  | 2020-03-30 |  |  |  |  | 2020-04-06 |  |  |  |  | 2020-04-13 |  |  |  |  | 2020-04-20 |  |  |  |  | 2020-04-27 |  |  |  |  | 2020-05-04 |  |  |  |  | 2020-05-11 |  |  |  |  | 2020-05-18 |  |  |  |  | 2020-05-25 |  |  |  |  | 2020-06-01 |  |  |  |  | 2020-06-08 |  |  |  |  | 2020-06-15 |  |  |  |  | 2020-06-22 |  |  |  |  | 2020-06-29 |  |  |  |  | 2020-07-06 |  |  |  |  | 2020-07-13 |  |  |  |  | 2020-07-20 |  |  |  |  | 2020-07-27 |  |  |  |  | 2020-08-03 |  |  |  |  | 2020-08-10 |  |  |  |  | 2020-08-17 |  |  |  |  | 2020-08-24 |  |  |  |  | 2020-08-31
 | time axis 2020-03-09 to 2020-09-04
1 | Contributor rights to Azure subcription(s) granted | ü | û |  | 2020-03-09 | 2020-03-06 | 0 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-02-06 | -21 | Actual | bar: 2020-03-09 to 2020-09-04
2 | Deployment and access to a Jumpbox located in the Datacenter with Local Administrator rights | ü | û |  | 2020-03-09 | 2020-02-05 | -22 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-02-05 | -22 | Actual | bar: 2020-03-09 to 2020-09-04
3 | VPN Access to Datacenter | ü | û | 4 | 2020-03-09 | 2020-03-16 | 6 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 6 | Actual | bar: 2020-03-09 to 2020-09-04
4 | Local server Administrator Credentials | ü | û | 5 | 2020-03-09 | 2020-02-12 | -17 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-02-12 | -17 | Actual | bar: 2020-03-09 to 2020-09-04
5 | VMWare VCenter Read Access Credentials | ü | û | 8 | 2020-03-09 | 2020-02-17 | -14 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-02-17 | -14 | Actual | bar: 2020-03-09 to 2020-09-04
6 | Change request for ASR system deployment | ü | û | 1 | 2020-03-09 | 2020-01-15 | -37 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-01-15 | -37 | Actual | bar: 2020-03-09 to 2020-09-04
7 | Azure Virtual Data Center Design | ü | û |  | 2020-03-09 | 2020-03-20 | 10 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-20 | 10 | Actual | bar: 2020-03-09 to 2020-09-04
8 | Shared Services / Hub Resource Plan |  |  | 6 | 2020-03-09 | 2020-03-13 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-10 | 2020-03-23 | 10 | Actual | bar: 2020-03-09 to 2020-09-04
9 | Onboarding and Tenant process Development |  |  | 20 | 2020-03-09 | 2020-03-13 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-13 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
10 | Cloud Consumer Onboarding content |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
11 | Agile / DevOps Process evaluation |  |  | 15 | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
12 | Infrastructure as Code (IaC) practices and templates |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
13 | Policy & Guardrial Generation |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
14 | Reporting & Inventory |  |  |  | 2020-03-09 | 2020-03-12 | 3 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-12 | 3 | Actual | bar: 2020-03-09 to 2020-09-04
15 | Establish Cloud Center of Excellence / Council |  |  |  | 2020-03-09 | 2020-04-20 | 30 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-04-20 | 30 | Actual | bar: 2020-03-09 to 2020-09-04
16 | Develop Enterprise Strategy |  |  |  | 2020-03-09 | 2020-04-20 | 30 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-04-20 | 30 | Actual | bar: 2020-03-09 to 2020-09-04
17 | Establish roadmap and implementation plan |  |  |  | 2020-03-09 | 2020-03-23 | 10 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-23 | 10 | Actual | bar: 2020-03-09 to 2020-09-04
18 | Process Management |  |  |  | 2020-03-09 | 2020-03-23 | 10 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-23 | 10 | Actual | bar: 2020-03-09 to 2020-09-04
19 | Azure footprint and deployment for environment |  |  |  | 2020-03-09 | 2020-03-23 | 10 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-23 | 10 | Actual | bar: 2020-03-09 to 2020-09-04
20 | Complete vDC questionaire |  |  |  | 2020-03-09 | 2020-03-13 | 4 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-13 | 4 | Actual | bar: 2020-03-09 to 2020-09-04
21 | Functional and non-functional requirements, deployment method, rollback plan, environment design |  |  |  | 2020-03-09 | 2020-03-27 | 14 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-27 | 14 | Actual | bar: 2020-03-09 to 2020-09-04
22 | Review Network detailed design |  |  |  | 2020-03-09 | 2020-03-23 | 10 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-23 | 10 | Actual | bar: 2020-03-09 to 2020-09-04
23 | Review and Validate subsctiptions (1-5) |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
24 | Setup hub and spoke network |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
25 | Configure site-to-site VPN to on-prem | ü | û |  | 2020-03-09 | 2020-03-05 | -2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-05 | -2 | Actual | bar: 2020-03-09 to 2020-09-04
26 | Network Mapping Review | ü |  |  | 2020-03-09 | 2020-03-17 | 6 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-17 | 6 | Actual | bar: 2020-03-09 to 2020-09-04
27 | Review Hub and spoke implementation |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
28 | Review existing regional spoke deployments |  |  |  | 2020-03-09 | 2020-07-21 | 95 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-07-21 | 95 | Actual | bar: 2020-03-09 to 2020-09-04
29 | Monitoring and Performance Reviews |  |  |  | 2020-03-09 | 2020-07-21 | 95 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-07-21 | 95 | Actual | bar: 2020-03-09 to 2020-09-04
30 | Phase 1 |  |  |  | 2020-03-09 | 2020-04-06 | 20 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-04-06 | 20 | Actual | bar: 2020-03-09 to 2020-09-04
31 | Workload Design |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
32 | Tooling setup and configuration |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
33 | Workload Onboarding |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
34 | Replication |  |  |  | 2020-03-09 | 2020-03-19 | 8 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-19 | 8 | Actual | bar: 2020-03-09 to 2020-09-04
35 | Test Fail over | ü |  |  | 2020-03-09 | 2020-02-13 | -17 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-02-13 | -17 | Actual | bar: 2020-03-09 to 2020-09-04
36 | Validation |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
37 | Cut over | ü |  |  | 2020-03-09 | 2020-02-06 | -22 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-02-06 | -22 | Actual | bar: 2020-03-09 to 2020-09-04
38 | Architecture and Migration Review and sign off |  |  |  | 2020-03-09 | 2020-03-13 | 4 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-13 | 4 | Actual | bar: 2020-03-09 to 2020-09-04
39 | Opertational hand off |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
40 | Phase 2 |  |  |  | 2020-03-09 | 2020-04-06 | 20 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-04-06 | 20 | Actual | bar: 2020-03-09 to 2020-09-04
41 | Workload Design |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
42 | Tooling setup and configuration |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
43 | Workload Onboarding |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
44 | Replication |  |  |  | 2020-03-09 | 2020-03-19 | 8 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-19 | 8 | Actual | bar: 2020-03-09 to 2020-09-04
45 | Test Fail over | ü |  |  | 2020-03-09 | 2020-01-16 | -37 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-01-16 | -37 | Actual | bar: 2020-03-09 to 2020-09-04
46 | Validation |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
47 | Cut over | ü |  |  | 2020-03-09 | 2020-01-09 | -42 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-01-09 | -42 | Actual | bar: 2020-03-09 to 2020-09-04
48 | Architecture and Migration Review and sign off |  |  |  | 2020-03-09 | 2020-03-13 | 4 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-13 | 4 | Actual | bar: 2020-03-09 to 2020-09-04
49 | Opertational hand off |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
50 | Phase 3 |  |  |  | 2020-03-09 | 2020-04-06 | 20 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-04-06 | 20 | Actual | bar: 2020-03-09 to 2020-09-04
51 | Workload Design |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
52 | Tooling setup and configuration |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
53 | Workload Onboarding |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
54 | Replication |  |  |  | 2020-03-09 | 2020-03-19 | 8 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-19 | 8 | Actual | bar: 2020-03-09 to 2020-09-04
55 | Test Fail over | ü |  |  | 2020-03-09 | 2019-12-18 | -57 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2019-12-18 | -57 | Actual | bar: 2020-03-09 to 2020-09-04
56 | Validation |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
57 | Cut over | ü |  |  | 2020-03-09 | 2019-12-11 | -62 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2019-12-11 | -62 | Actual | bar: 2020-03-09 to 2020-09-04
58 | Architecture and Migration Review and sign off |  |  |  | 2020-03-09 | 2020-03-13 | 4 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-13 | 4 | Actual | bar: 2020-03-09 to 2020-09-04
59 | Opertational hand off |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
60 | Phase 4 |  |  |  | 2020-03-09 | 2020-04-06 | 20 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-04-06 | 20 | Actual | bar: 2020-03-09 to 2020-09-04
61 | Workload Design |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
62 | Tooling setup and configuration |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
63 | Workload Onboarding |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
64 | Replication |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
65 | Test Fail over | ü |  |  | 2020-03-09 | 2019-11-20 | -77 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2019-11-20 | -77 | Actual | bar: 2020-03-09 to 2020-09-04
66 | Validation |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
67 | Cut over | ü |  |  | 2020-03-09 | 2019-11-13 | -82 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2019-11-13 | -82 | Actual | bar: 2020-03-09 to 2020-09-04
68 | Architecture and Migration Review and sign off |  |  |  | 2020-03-09 | 2020-03-13 | 4 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-13 | 4 | Actual | bar: 2020-03-09 to 2020-09-04
69 | Opertational hand off |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
70 | Phase 5 |  |  |  | 2020-03-09 | 2020-04-06 | 20 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-04-06 | 20 | Actual | bar: 2020-03-09 to 2020-09-04
71 | Workload Design |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
72 | Tooling setup and configuration |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
73 | Workload Onboarding |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
74 | Replication |  |  |  | 2020-03-09 | 2020-03-19 | 8 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-19 | 8 | Actual | bar: 2020-03-09 to 2020-09-04
75 | Test Fail over | ü |  |  | 2020-03-09 | 2019-10-23 | -97 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2019-10-23 | -97 | Actual | bar: 2020-03-09 to 2020-09-04
76 | Validation |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
77 | Cut over | ü |  |  | 2020-03-09 | 2019-10-16 | -102 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2019-10-16 | -102 | Actual | bar: 2020-03-09 to 2020-09-04
78 | Architecture and Migration Review and sign off |  |  |  | 2020-03-09 | 2020-03-13 | 4 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-13 | 4 | Actual | bar: 2020-03-09 to 2020-09-04
79 | Opertational hand off |  |  |  | 2020-03-09 | 2020-03-11 | 2 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-11 | 2 | Actual | bar: 2020-03-09 to 2020-09-04
80 | Documentation Closure and review |  |  |  | 2020-03-09 | 2020-03-16 | 5 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-16 | 5 | Actual | bar: 2020-03-09 to 2020-09-04
81 | Documentation Sign off | ü |  |  | 2020-03-09 | 2020-03-10 | 1 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-10 | 1 | Actual | bar: 2020-03-09 to 2020-09-04
82 | Engagement Review |  |  |  | 2020-03-09 | 2020-03-10 | 1 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-10 | 1 | Actual | bar: 2020-03-09 to 2020-09-04
83 | Migraion Clean up |  |  |  | 2020-03-09 | 2020-03-10 | 1 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-10 | 1 | Actual | bar: 2020-03-09 to 2020-09-04
84 | Sample Milestone | ü |  |  | 2020-03-09 | 2020-03-13 | 4 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-03-13 | 4 | Actual | bar: 2020-03-09 to 2020-09-04
85 | Sample Activity 13 |  |  |  | 2020-03-09 | 2020-04-06 | 20 | Planned | bar: 2020-03-09 to 2020-09-04
[5 empty] | 2020-03-09 | 2020-04-06 | 20 | Actual | bar: 2020-03-09 to 2020-09-04
[5 empty] | ü | Milestone |  |  | 2020-03-12: Planned; 2020-03-19: Actual / Projected
[5 empty] | û | Client Work

## Staffing Plan
| Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6
WEEKS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total Hours | Rate Used | Total
Roles | PROJECT OVERSIGHT
Delivery Director | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 240 | 275 | 66000
Solution Architect | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 360 | 300 | 108000
Phase 1 - Solution Architecture & Migration Planning
Application Architect | 40 | 40 | 40 | 40 | 40 | 40 | [6 empty] | 240 | 300 | 72000
Application Engineer | 40 | 40 | 40 | 40 | [8 empty] | 160 | 250 | 40000
Phase 1 - Single Domain Migration
Application Architect | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 300 | 72000
Application Engineer |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 320 | 250 | 80000
Application(QA) Engineer |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 320 | 250 | 80000
Cloud Automation Engineer |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 320 | 250 | 80000
598000

## Issues Log
Project: |  | Sample Client - Enterprise Cloud Transformation
Project Manager: |  | Sample Managers Name
# | Work Stream | Type | Category | Title | Description | Date Raised | Owner | Due Date | Current State | Date Closed | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Change Requests
Project: |  | Sample Client - Enterprise Cloud Transformation
Project Manager: |  | Sample Managers Name
CR# | Change Description | Affected Component(s) | Type of Change | Priority | Originator | Date Submitted | Owner | Status | Notes/Status History | Approved for Release #
1
2
3
4
5

## Rejected CRs
Project: |  | Sample Client - Enterprise Cloud Transformation
Project Manager: |  | Sample Managers Name
CR# | Change Description | Affected Component(s) | Type of Change | Originator | Date Submitted | Owner | Status | Notes/Status History

## Large Scale Migration
Program level team
| 40 | Lead Architect
| 40 | Program Manager
| 40 | Migration Architect ( Across 2 - 3 migration teams )
|  |  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Migration Architect (40), CMC Lead (40) |  | Team 1 - 300 servers per month |  | Kick off
| 40 | Technical BA |  |  | Group 1 - 10 Servers |  |  |  | Group 5 - 100 Servser |  |  |  | Group 9 - 100 Servser |  |  |  |  | Move Group 9
| 40 | CMC Engineer |  |  | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover |  | Archeology | Review/Replicate | Non-Prod | Production | Support
| 40 | DD/DM |  |  |  | Group 2 - 30 Servers |  |  |  | Group 6 - 100 Servser
[6 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
[7 empty] | Group 3 - 50 Servers |  |  |  | Group 7 - 100 Servser
[7 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
[8 empty] | Group 4 - 80 Servers |  |  |  | Group 8 - 100 Servser
[8 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
|  | Team 2 - 300 Serves per month |  |  |  | Kick off
| 40 | Technical BA |  |  |  |  | Group 1 - 10 Servers |  |  |  | Group 5 - 100 Servser |  |  |  | Group 9 - 100 Servser
| 40 | CMC Engineer |  |  |  |  | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
| 40 | DD/DM | [5 empty] | Group 2 - 30 Servers |  |  |  | Group 6 - 100 Servser
[8 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
[9 empty] | Group 3 - 50 Servers |  |  |  | Group 7 - 100 Servser
[9 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
[10 empty] | Group 4 - 80 Servers |  |  |  | Group 8 - 100 Servser
[10 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
|  | Team 3 - 300 Servers per month | [5 empty] | Kick off
| 40 | Technical BA | [6 empty] | Group 1 - 10 Servers |  |  |  | Group 5 - 100 Servser |  |  |  | Group 9 - 100 Servser
| 40 | CMC Engineer | [6 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
| 40 | DD/DM | [7 empty] | Group 2 - 30 Servers |  |  |  | Group 6 - 100 Servser
[10 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
[11 empty] | Group 3 - 50 Servers |  |  |  | Group 7 - 100 Servser
[11 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
[12 empty] | Group 4 - 80 Servers |  |  |  | Group 8 - 100 Servser
[12 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
|  | Epic | [5 empty] | Definition
SAP
Architect
HA
DR
Firewall
Networking
BA
Capture aplication specifics
Docments existing environment

## Single Team Migration
|  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
| Team 1 - 300 servers per month |  | Kick off
40 | Technical BA |  |  | Group 1 - 10 Servers |  |  |  | Group 5 - 100 Servser |  |  |  | Group 9 - 100 Servser
40 | CMC Engineer |  |  | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
40 | DD/DM |  |  |  | Group 2 - 30 Servers |  |  |  | Group 6 - 100 Servser
40 | CMC Lead |  |  |  | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
[6 empty] | Group 3 - 50 Servers |  |  |  | Group 7 - 100 Servser
[6 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
[7 empty] | Group 4 - 80 Servers |  |  |  | Group 8 - 100 Servser
[7 empty] | Onboarding | Definition/Replication |  | Cutover | Onboarding | Definition/Replication |  | Cutover
| Epic | [5 empty] | Definition
SAP
Architect
HA
DR
Firewall
Networking
BA
Capture aplication specifics
Docments existing environment

## Decisions
Project: |  | Sample Client - Enterprise Cloud Transformation
Project Manager: |  | Sample Managers Name
# | Description of Decision | Background | Outcome
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Assumtion Log
Project: |  | Sample Client - Enterprise Cloud Transformation
Project Manager: |  | Sample Managers Name
# | Assumption Category | Assumption Description | Owner(s)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Communication Plan
Project: | Sample Client - Enterprise Cloud Transformation
Project Manager: | Sample Managers Name
Meeting Name | Lead / Author (who prepares) | Audience | Purpose | Frequency | Method / Format | Notes
Project Kickoff - External Team | Project Manger | Project Sponsor(s) Business Owner(s) SMEs Other Client Leads Project Manager | * Share Project Objective, Scope, project's success factors * Roles and responsibilities * Share other information such as what details will be communicated and how * Share timeline if applicable | Project Initiation | Meeting | TBD - Not yet scheduled
Project Kickoff - Internal Team | Project Manger | Project Team | * Set expectations and ground rules with the team (Logistics, team norms, dos & don'ts) * Level set the team to the project's success factors * Review roles and responsibilities | Project Initiation | Meeting | TBD - Not yet scheduled
Daily Standup | Project Manager / Leads | Project Team | * Focus on progress on previous day, planned for the day and issues/obstacles from completing tasks. * Leave the standup with owners for issues, don't try to solve the issues during the standup. | Daily | Standup Meeting | This meeting is held daily at 9:30AM. Location is <conference/team room location>.
Team Project Status | Project Manager | Project Manager Leads | * Obtain a detailed update from the lead from each subteam to prepare for weekly project status. * Review risks and issues to determine which to address in project status | Weekly | Meeting
Executive Project Status | Project Manger | Project Sponsor(s) Business Owner(s) Project Manager | * Review Progress to plan * Review open issues & risks * Review open change requests * Identify decision makers / owners for action items. | Weekly | Meeting | Scheduled for <day> at <time> AM/PM
Change Request Review | Project Manager Lead BA | Project Sponsor Business Owner | Review open and new Change Requests | As Needed | Meeting | Follow project change control process
Decisions / Changes | Project Manager / Leads | All | When decisions are made (especially those that are different from the original assumptions), follow-up with an email explaining the situation, decision and impact if any. | As Needed | Email
Steering Committee | Project Manager | Project Sponsor(s) Business Owner(s) | Review overall project health with project stakeholders | Monthly | Meeting | TBD - Not yet scheduled

## RACI
Phase | Project Task | Delivery Manager | Delivery Director | EA | SA | Tech Lead | Eng. | BDM | Cons. Ops | Alliance Support | Community Leader | KM Leader | Client | Notes captured for any deviations from this default RACI as part of Internal Mobilization. This sheet should be saved in the project admin folder for this engagement if yes to refer back to later.
Project Conception | Introduce Delivery Management to client for project conception phase | C | C |  | C |  |  | A/R |  |  |  |  | C
Project Conception | Execute client readiness review for start date |  | A/R |  | I |  |  | C |  |  |  |  | C
Project Conception | Partner with Consulting Operations for resource assignment | I | A/R |  | C |  |  | I | C
Project Conception | Provide technical skills and resource role types/levels | I | A |  | R |  |  |  | C
Project Conception | Updated purple forecast with start date | R | A |  | I |  |  | I | C |  |  |  | C
Project Conception | Validate schedule forecast to MSFT funding deadlines | R | A |  |  | C |  | I |  | I |  |  | I
Internal Mobilization | Reconfirm start date | R | A |  |  | I | I | I | I | I |  |  | C
Internal Mobilization | Assess to original staffing plan | R | A |  |  | C |  |  | C
Internal Mobilization | Prepare client/project summary | R | A |  | C |  |  | C
Internal Mobilization | Setup project tools (Harvest, Jira, etc.) | R | A |  | I | C | I
Internal Mobilization | Setup KT and warm hand off sales-delivery meeting | R | A |  | C | C | I | C
Internal Mobilization | Execute KT and warm hand off sales-delivery meeting | R | A |  | C | C | I | C
Internal Mobilization | Review RACI and discuss/confirm ownership of Project Tasks aligned to the RACI | C | A/R |  |  | C
Client Launch | Prepare project kickoff presentation | R | A |  | C | C | I | I
Client Launch | Schedule client/10M project kickoff | R | A |  | C | C | C | C
Client Launch | Plan and Execute client/10M project kickoff | C | A/R |  | C | C | I | C |  |  |  |  | C
Client Launch | Update 10M to the Partner of Record (DPOR) | I | R |  | I | C | C | A |  | I |  |  | I
Execute Project | Scope: Manage to project deliverables and outcomes | R | A |  |  | C | C | I |  |  |  |  | I
Execute Project | Schedule: Maintain project plan and execution status "Earn" | R | A |  |  | C | C | I |  |  |  |  | I
Execute Project | Cost: Manage forecast and budget tracking "Burn" | R | A |  |  | C | C | I |  |  |  |  | I
Execute Project | Execute overall technical vision, strategy and direction for the big picture - overall outcome / result / solution | I | I | A/R | C | C
Execute Project | Facilitate, support, and drive the customer's technical direction and decision-making | I | I | A/R | C | C
Execute Project | Overall Azure subscription visioning, design, and implementation | I | I | A/R | C | C
Execute Project | Decomposition of SOW/Deliverables to tasks and engineering work | I | I |  | I | A/R | C
Execute Project | Sprint planning | C | C |  | I | A/R | C | [5 empty] | I
Execute Project | Backlog ownership - stories, sprint plans, develop and assign tasks | C | C |  |  | A/R | I
Execute Project | Backlog management - task coordination, hours tracked and married to the overall project plan | R | A |  |  | C | I
Execute Project | Create overall project plan and schedule with sprint plan and any other project dependencies and tasks | R | A |  | C | C | I | [5 empty] | I
Execute Project | Validate balance of scope, schedule, cost and outcomes between the overall project plan and the technical sprint plan input | R | A |  |  | C
Execute Project | Comprehension of technical requirements to meet deliverables and ability to assign work |  |  |  |  | A/R | C
Execute Project | Understand skills and level of experience for Engineers staffed on the engagement to ascertain level of TL support | I | I |  |  | A/R | C
Execute Project | Define success measures and outcomes for Engineers executing on the engagement | I | I |  |  | A/R | C
Execute Project | Schedule meetings and workshops ongoing cadence (internal and combined internal/external) | R | A |  | C | C | C | [5 empty] | C
Execute Project | Align 10M technical tasks, domains and the relationship of those to other areas of the engagement |  | I |  | C | A/R | C
Execute Project | Assign and communicate Epic/Story/Task to Engineers | I | I |  |  | A/R | C
Execute Project | Setup and facilitate meetings and workshops | R | A |  | I | C | C | [5 empty] | C
Execute Project | Setup and facilitate status and stand-up meetings | R | A |  | I | C | C | I |  |  |  |  | C
Execute Project | Create client status report: scope, schedule, cost, risks, blockers | C | A/R |  |  | C | I
Execute Project | Provide and input information and content for status report (technical) | I | I |  |  | A/R | C
Execute Project | Provide and input information and content for status report (engagement: scope schedule cost; risks issues blockers) | R | A |  |  | C
Execute Project | Review compiled status report for accuracy and quality | C | A/R |  |  | C
Execute Project | Present in status meeting | I | A/R |  |  | R | [6 empty] | I
Execute Project | Own overall flow of meeting to cover both "big picture" and next steps/action items | I | A/R |  |  | C
Execute Project | Complete project deliverables to SOW | I | A |  |  | R | C
Execute Project | Develop technical documentation as part of scope | I | A |  |  | R | C
Execute Project | Technical quality review and alignment with best practices | I | I |  |  | A/R | C
Execute Project | Execute assigned tasks, update status of tasks to DM or tool, enter hours against assigned tasks/project in Harvest | I | I |  |  | A | R
Execute Project | Contribute to technical work effort for self-assigned assignments, filling in around Engineering, and/or supporting | I | I |  |  | A/R | C
Execute Project | Set and manage customer technical and deployment expectations | I | I |  |  | A/R | R | [5 empty] | I
Execute Project | Set and manage customer engagement expectations balancing scope, schedule, and budget available | R | A |  |  | C | I | [5 empty] | I
Execute Project | Document meeting minutes, action items and general tracking | R | A |  |  | I | I | [5 empty] | I
Execute Project | Manage change control of scope with internal/external teams | R | A |  |  | C | I | [5 empty] | I
Execute Project | Manage engagement level risks and issues to closure | R | A |  |  | C | C | C |  |  |  |  | I
Execute Project | Identify and mitigate technical leval risks and issues to closure | C | C |  |  | A/R | C | [5 empty] | I
Execute Project | Coach and mentor the technical maturity of Engineers |  |  |  |  | A/R | C
Execute Project | Bridge communication and information between customer and Engineering team | I | I |  |  | A/R | C | [5 empty] | I
Execute Project | Bridge communication and any necessary escalations between customer, 10M, and Sales/Account Development | I | A/R |  |  |  |  | C |  |  |  |  | I
Execute Project | Communicate and educate on technical decisions within the execution of the delivery scope | I | C |  |  | A/R | C | [5 empty] | I
Execute Project | Manage and develop buyer and decision maker customer relationships | C | A/R |  |  | C |  | I |  |  |  |  | I
Execute Project | Day to day management of technical team members |  |  |  |  | A/R | C | [5 empty] | I
Close | Knowledge Transfer to Client team | I | A |  | I | R | C | I |  |  |  |  | C
Close | Internal review of deliverables coordination-completion | C | C |  |  | A/R | C
Close | External review and provide deliverables to client | C | C |  |  | A/R | I | I |  |  |  |  | C
Close | Validate/update 10M to the Partner of Record (DPOR) | I | R |  | I | C | C | A |  | I |  |  | I
Close | Execute close meeting with client team | R | A |  |  | C | I | I |  |  |  |  | C
Close | Send client survery | R | A |  | I | I | I | I
Close | Execute Engagement Results reviews for delivery individuals | C | A/R |  |  | A/R | C
Close | Execute deliverable review and provide to 10M KM library | R | A |  |  | A | R |  |  |  | C | C
Close | Execute lessons learned retrospective for continuous improvement | R | A |  | C | C | C | C

## Holidays
Holiday | Date
New Years | 2021-01-01
Memorial Day | 2020-05-25
Independence Day | 2020-07-04
Labor Day | 2020-09-07
Thanksgiving | 2020-11-26
Thanksgiving | 2020-11-27
Christmas | 2019-12-25
Holiday Party | 2020-01-11
Boat Party
MSFT Conference Day 1
MSFT Conference Day 2
MSFT Conference Day 3
1oth Company Meeting
* Besure to add in 10th day like boat event or MSFT conferences