## Sheet1
2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32
Pilot
| Archeology | Review/Replicate | Non-Prod | Production | Support
Migration Group 1
|  |  | Archeology | Review/Replicate | Non-Prod | Production | Support | Support
Migration Group 2
[5 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 3
[6 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 4
[7 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 5
[8 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 6
[9 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 7
[10 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 8
[11 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 9
[12 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 10
[13 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 11
[14 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 12
[15 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 13
[16 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 14
[17 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 15
[18 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 16
[19 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 17
[20 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 18
[21 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 19
[22 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 20
[23 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 21
[24 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 22
[25 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
Migration Group 23
[26 empty] | Archeology/Review/Replicate | Non-prod | Production | Support
We are here.

## Sheet2
Pilot
Archeology | Review/Replicate | Non-Prod | Production | Support
asdfasdflkj | ;lkj;klj
asdfasdflkj | ;lkj;lkj | 1 | 1
asdfasdflkj | ;lkj;lkj
asdfasdflkj
|  | 54 | 54