## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 8/4/2020
Blockers / Challenges
Improvement Items
Migration
Upcoming
Projects
4
Sandler Travis (STTAS)
Bass Pro
Elekta
Providence
2
Hussmann (LZ)
Flow Intl (LZ)
Hours & Forecast
Service Expansion
  In-Progress:
  Azure VMware Solution
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Estee – Awaiting change freeze to be lifted to perform partial DR test and handover. Marshall taking lead on this one. Scheduled for end of August.
Bass Pro still moving slowly but should ramp up when they give us control of the migrations.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 4 | 4 | 4 | 6 | 6 | 7
Mig VMs | 1 | 6 | 34 | 36 | N/P | N/P
Mig DBs | 0 | 0 | 0 | N/P | N/P | N/P
Other Work | 1 | 0 | 0 | N/P | N/P | N/P
Rolling Off / On Hold
1
Estee
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
34
Resources Scheduled
To Migrate
This week so far
-
Landing Zone
-
0
See next slide for details
BassPro should be ramping up in a few weeks, they’ve added some new apps and servers to the scope
Elekta will likely have to be reduced in a week or two until migrations get started
Providence should start ramping up in the next week or two

## Slide 3
Cloud Service Center Metrics
CMC Utilization %
Forecast
Work Items by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
STTAS | 0 | 0 | 0 | 0
BassPro | 1 | 6 | 28 | 36
Providence | 0 | 4 | 4 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out | Three Weeks Out
Percent Utilized | 0.79032 | 0.75 | 0.95161 | 1.0448 | 1.097 | 1.1458
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 1 | 6 | 28 | 36
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.67339 | 0.89113
Joe/Kyle billable 5-10hrs/wk+