## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 8/11/2020
Blockers / Challenges
Improvement Items
Migration
Upcoming
Projects
4
Sandler Travis (STTAS)
Bass Pro
Elekta
Providence
7
Hussmann (LZ)
Flow Intl (LZ)
Samaritan (LZ)
Panasonic (LZ)
CDW (LZ)
Stone (LZ)
Substantial (LZ)
Hours & Forecast
Service Expansion
  In-Progress:
  Azure VMware Solution
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Estee – Awaiting change freeze to be lifted to perform partial DR test and handover. Marshall taking lead on this one. Scheduled for end of August.
Bass Pro – need additional migrations scheduled to keep momentum. Nothing scheduled past this week.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 4 | 4 | 4 | 8 | 9 | 7
Mig VMs | 6 | 32 | 13 | N/P | N/P | N/P
Mig DBs | 0 | 0 | 0 | N/P | N/P | N/P
Other Work | 0 | 0 | 0 | N/P | N/P | N/P
Rolling Off / On Hold
1
Estee
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
13
Resources Scheduled
To Migrate
This week so far
-
Landing Zone
-
0
See next slide for details
BassPro is ramping up, and will likely get extended due to the remaining budget
Elekta will likely have to be reduced in a week or two until migrations get started
Providence should start ramping up in the next week or two

## Slide 3
Cloud Service Center Metrics
CMC Utilization %
Forecast
Work Items by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
STTAS | 0 | 0 | 0 | 0
BassPro | 6 | 28 | 13 | 0
Providence | 0 | 4 | 0 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out | Three Weeks Out
Percent Utilized | 0.75 | 0.95161 | 1.0323 | 1.0486 | 1.3264 | 1.3542
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 6 | 32 | 13 | 0
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.89113 | 0.95161
Joe/Kyle billable 5-10hrs/wk+