## Slide 1
Updates / New Items
10M – Cloud Service Center
Blockers / Challenges
Improvement Items
Active
Upcoming
Projects
4
Estee
Bacardi
Noble Drilling
CNB
2
Bass Pro
Sandler Travis
Hours & Forecast
Service Expansion
  In-Progress:
  SQL Server Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  Other Deployments as Needed
    WVD?
Bass Pro
Deloitte
Assurant
Need update on Sandler Travis status, hasn’t kicked off yet.
ELC – high burn, but still complex workloads left to migrate. May not have enough hours to complete.
CNB – minimal to no progress; waiting on client
Noble - No clear schedule for migrations.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast | 115 | 118 | 105 | 45 | 55 | 75
Actual |  |  |  |  |  | 
% |  |  |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 4 | 4 | 4 | 3 | 3 | 4
Mig VMs | 1 | 1 | 26 | 4 | N/P | N/P
Mig DBs | 0 | 3 | 0 | N/P | N/P | N/P
Rolling Off / Closing
1
Assurant
81%
Utilized
This week
Based on forecast
Migration automation
  Full end to end automation
  Additional operations setup automation
  Getting the team to actually use the automation!
Sales Support
Tech Support
26
Resources Migrating
Scheduled this
week so far

## Slide 2
Cloud Service Center Graphs
CMC Utilization %
based on forecast
Migrated Resources by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
Estee | 0 | 0 | 26 | 0
CNB | 0 | 0 | 0 | 4
Bacardi | 1 | 4 | 0 | 0
Noble | 0 | 0 | 0 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out
Percent Utilized | 0.88462 | 0.90769 | 0.80769 | 0.34615 | 0.42308
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 1 | 1 | 26 | 4
DB | 0 | 3 | 0 | 0