## Slide 1
Updates / New Items
10M – Cloud Service Center
Blockers / Challenges
Improvement Items
Active
Upcoming
Projects
4
Estee
Noble Drilling
CNB
Sandler Travis (STTAS)
1
Bass Pro
Hours & Forecast
Service Expansion
  In-Progress:
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Bass Pro
Deloitte
CNB still has a workload left to migrate, but little budget to work with and no planning has been completed. Working to get back on track.
ELC – high burn, but still complex workloads left to migrate. May not have enough hours to complete.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast Hours | 105 | 71 | 41 | 54 | 54 | 60
Actual Hours | 144.5 | 121.8 |  |  |  | 
Actual % Utilized | 117% | 98% |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 4 | 4 | 4 | 3 | 3 | 3
Mig VMs | 12 | 2 | 11 | 24 | N/P | N/P
Mig DBs | 0 |  | 0 | N/P | N/P | N/P
Rolling Off / Closing
1
Bacardi
33%
Utilized
This week
Based on forecast
Includes Marshall**
Dropping Marshall Next Week
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
Sales Support
Tech Support
11
Resources Scheduled
To Migrate
This week so far

## Slide 2
Cloud Service Center Metrics
CMC Utilization %
Forecast
Migrated Resources by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
Estee | 12 | 0 | 2 | 14
CNB | 0 | 0 | 4 | 0
Bacardi | 0 | 0 | 0 | 0
Noble | 0 | 2 | 5 | 8
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out
Percent Utilized | 0.84677 | 0.57258 | 0.33065 | 0.43548 | 0.43548
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 12 | 2 | 11 | 24
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 1.1653 | 0.98226