## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 4/7/2020
Blockers / Challenges
Improvement Items
Active
Upcoming
Projects
4
Estee
Noble Drilling
CNB
Sandler Travis (STTAS)
1
Bass Pro
Hours & Forecast
Service Expansion
  In-Progress:
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Bass Pro
Deloitte
CNB still has a workload left to migrate, but little budget to work with. Customer having a hard time planning and completing prereq work.
ELC – CP/VP of Sales need communication to get SharePoint migration scheduled.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast Hours | 71 | 42 | 39 | 49 | 40 | 45
Actual Hours | 121.8 | 60 |  |  |  | 
Actual % Utilized | 98% | 48% |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 4 | 4 | 4 | 4 | 3 | 3
Mig VMs | 2 | 14 | 6 | 4 | 14 | N/P
Mig DBs | 0 | 0 | 0 | N/P | N/P | N/P
Rolling Off / Closing
-
-
42%
Utilized
This week
Based on forecast
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
Sales Support
Tech Support
6
Resources Scheduled
To Migrate
This week so far

## Slide 2
Cloud Service Center Metrics
CMC Utilization %
Forecast
Migrated Resources by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
Estee | 0 | 2 | 1 | 0
CNB | 0 | 0 | 0 | 4
Noble | 2 | 12 | 5 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out
Percent Utilized | 0.57258 | 0.33871 | 0.42391 | 0.53261 | 0.43478
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 2 | 12 | 7 | 4
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.98226 | 0.48387