## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 4/14/2020
Blockers / Challenges
Improvement Items
Active
Upcoming
Projects
5
Estee
Noble Drilling
CNB
Sandler Travis (STTAS)
Kraft/Heinz
1
Bass Pro
Hours & Forecast
Service Expansion
  In-Progress:
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Bass Pro
Deloitte
CNB still has a workload left to migrate, but little budget to work with. Customer having a hard time planning and completing prereq work.
ELC – CP/VP of Sales need communication to get SharePoint and remaining migrations scheduled.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast Hours | 42 | 39 | 26 | 45 | 45 | 20
Actual Hours | 60 | 27.5 |  |  |  | 
Actual % Utilized | 48% | 30% |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 4 | 4 | 5 | 5 | 4 | 4
Mig VMs | 14 | 6 | 6 | 5 | 14 | N/P
Mig DBs | 0 | 0 | 0 | N/P | N/P | N/P
Rolling Off / Closing
-
-
28%
Utilized
This week
Based on forecast
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
Sales Support
Tech Support
6
Resources Scheduled
To Migrate
This week so far
Deloitte

## Slide 2
Cloud Service Center Metrics
CMC Utilization %
Forecast
Migrated Resources by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
Estee | 2 | 0 | 0 | 1
CNB | 0 | 0 | 0 | 4
Noble | 12 | 6 | 6 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out
Percent Utilized | 0.45652 | 0.42391 | 0.28261 | 0.48913 | 0.48913
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 12 | 6 | 6 | 5
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.65217 | 0.29891