## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 4/21/2020
Blockers / Challenges
Improvement Items
Active
Upcoming
Projects
5
Estee
Noble Drilling
CNB
Sandler Travis (STTAS)
Kraft/Heinz
1
Bass Pro
Bacardi
Hours & Forecast
Service Expansion
  In-Progress:
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Bass Pro
Deloitte
CNB still has a workload left to migrate, but little budget to work with. Customer having a hard time planning and completing prereq work.
ELC – SharePoint is the only workload left from the SoW. Running low on hours – we likely have enough hours to complete the migration, but not to participate in the hyper-care support following.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast Hours | 39 | 26 | 20 | 15 | 30 | 20
Actual Hours | 27.5 | 28.5 |  |  |  | 
Actual % Utilized | 30% | 31% |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 4 | 5 | 5 | 5 | 4 | 4
Mig VMs | 6 | 7 | 1 | 18 | N/P | N/P
Mig DBs | 0 | 0 | 0 | N/P | N/P | N/P
Rolling Off / Closing
-
-
22%
Utilized
This week
Based on forecast
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
Sales Support
Tech Support
1
Resources Scheduled
To Migrate
This week so far
Deloitte

## Slide 2
Cloud Service Center Metrics
CMC Utilization %
Forecast
Migrated Resources by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
Estee | 0 | 1 | 0 | 14
CNB | 0 | 0 | 0 | 4
Noble | 6 | 6 | 1 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out
Percent Utilized | 0.42391 | 0.28261 | 0.21739 | 0.16304 | 0.32609
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 6 | 7 | 1 | 18
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.29891 | 0.30978