## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 4/28/2020
Blockers / Challenges
Improvement Items
Active
Upcoming
Projects
5
Estee
CNB
Sandler Travis (STTAS)
Kraft/Heinz
Bacardi
1
Bass Pro
Hours & Forecast
Service Expansion
  In-Progress:
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Bass Pro
Deloitte
Continue to have trouble getting DD/DMs to properly enter forecast.
CNB E3 migration on hold for at least a week.
ELC – SharePoint is the only workload left from the SoW. Running low on hours – we likely have enough hours to complete the migration, but not to participate in the hyper-care support following.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast Hours | 26 | 21 | 15 | 5 | 30 | 60
Actual Hours | 28.5 | 15 |  |  |  | 
Actual % Utilized | 31% | 16% |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 5 | 5 | 5 | 4 | 4 | 4
Mig VMs | 7 | 2 | 14 | 2 | 4 | N/P
Mig DBs | 0 | 0 | 0 | N/P | N/P | N/P
Rolling Off / Closing
1
Noble Drilling
16%
Utilized
This week
Based on forecast
CMC engineer billing – I suspect the engineers are not accounting for all of their billable hours in Harvest. Will start discussion and coach them.
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
Sales Support
Tech Support
14
Resources Scheduled
To Migrate
This week so far
Deloitte
Forecast not correct

## Slide 2
Cloud Service Center Metrics
CMC Utilization %
Forecast
Migrated Resources by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
Estee | 1 | 0 | 14 | 0
CNB | 0 | 0 | 0 | 0
Noble | 6 | 1 | 0 | 0
STTAS | 0 | 2 | 0 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out
Percent Utilized | 0.28261 | 0.22826 | 0.16304 | 0.054348 | 0.32609
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 7 | 2 | 14 | 2
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.30978 | 0.16304