## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 5/5/2020
Blockers / Challenges
Improvement Items
Active
Upcoming
Projects
5
Estee
CNB
Sandler Travis (STTAS)
Kraft/Heinz
Bacardi
1
Bass Pro
Hours & Forecast
Service Expansion
  In-Progress:
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Bass Pro
Deloitte
CNB E3 migration is still not progressing. They continue to struggle on their end.
ELC - Waiting on change requests to complete the CPM/CMAT DR and close out the SoW.
ELC - They’re asking us to re-migrate Kofax as they rolled it back after several weeks in Azure. Not sure if we actually have hours to do this….
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast Hours | 21 | 66 | 45 | 75 | 115 | 60
Actual Hours | 15 | 91 |  |  |  | 
Actual % Utilized | 16% | 99% |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 5 | 5 | 5 | 4 | 4 | 4
Mig VMs | 2 | 29 | 5 | N/P | N/P | N/P
Mig DBs | 0 | 0 | 0 | N/P | N/P | N/P
Rolling Off / Closing
1
Noble Drilling
49%
Utilized
This week
Based on forecast
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
Sales Support
Tech Support
5
Resources Scheduled
To Migrate
This week so far
Deloitte

## Slide 2
Cloud Service Center Metrics
CMC Utilization %
Forecast
Migrated Resources by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
Estee | 0 | 14 | 0 | 0
CNB | 0 | 0 | 0 | 0
Noble | 1 | 0 | 0 | 0
STTAS | 2 | 0 | 0 | 0
Bacardi | 0 | 15 | 0 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out
Percent Utilized | 0.22826 | 0.71739 | 0.48913 | 0.81522 | 1.25
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 2 | 29 | 0 | 0
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.16304 | 0.98913