## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 6/16/2020
Blockers / Challenges
Improvement Items
Migration
Upcoming
Projects
6
Estee
CNB
Sandler Travis (STTAS)
Bass Pro
2
Elekta
Providence
Hours & Forecast
Service Expansion
  In-Progress:
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Resources – Marshall transition and forecasted
CNB E3 migration issues appear to be resolved. Awaiting scheduling to perform migration.
Estee - Still performing work. Working through remaining issues and prereqs to complete DR setup for CPM and CMAT. Rehan added forecast to make the work visible.
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast Hours | 55 | 37 | 125 | 135 | 92 | ?
Actual Hours | 43 | 46.8 |  |  |  | 
Actual % Utilized | 47% | 51% |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 6 | 6 | 6 | 5 | 5 | 4
Mig VMs | 1 | 0 | 1 | N/P | N/P | N/P
Mig DBs | 2 | 0 | 1 | 4 | N/P | N/P
Other Work | 2 | 3 | 0 | N/P | N/P | N/P
Rolling Off
2
KraftHeinz
Bacardi
136%
Utilized
This week
Based on forecast
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
1
Resources Scheduled
To Migrate
This week so far
Deloitte (AME-AI)
Landing Zone
Children’s Health Center
Santa Clara County OE
1

## Slide 2
Cloud Service Center Metrics
CMC Utilization %
Forecast
Work Items by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
Estee | 0 | 1 | 1 | 0
CNB | 0 | 0 | 0 | 4
STTAS | 1 | 0 | 1 | 0
Bacardi | 1 | 0 | 0 | 0
Childrens | 0 | 0 | 1 | 1
SCCOE | 0 | 1 | 1 | 1
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out | Three Weeks Out
Percent Utilized | 0.59783 | 0.40217 | 1.3587 | 1.4674 | 1 | 0.86957
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 1 | 2 | 1 | 0
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.46739 | 0.5087