## Slide 1
Updates / New Items
Cloud Service Center Dashboard- 6/30/2020
Blockers / Challenges
Improvement Items
Migration
Upcoming
Projects
5
Estee
Sandler Travis (STTAS)
Bass Pro
Elekta
Providence
0
-
Hours & Forecast
Service Expansion
  In-Progress:
  Azure VMware Solution
  SQL Server/DB Migration Enhancements
  Managed Services Transition
  ALZ Engineering/Deployment
  WVD Quickstart Deployments
Resources – Marshall transition and forecasted hours. Overallocated hourse 2-6 weeks out.
Estee – CMAT DR setup and testing complete. CPM DR not able to fully complete due to change freeze. Will perform partial test and handover.
Forecast continues to be a problem with Bass Pro
Support
Stats
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Forecast Hours | 125 | 118 | 78 | 103 | 173 | 168
Actual Hours | 88.5 | 49 |  |  |  | 
Actual % Utilized | 96% | 49% |  |  |  | 
 | 2 weeks ago | Last Week | This Week | Next Week | 2 weeks out | 3 weeks out
Projects | 6 | 6 | 6 | 5 | 5 | 4
Mig VMs | 2 | 4 | 2 | N/P | N/P | N/P
Mig DBs | 0 | 0 | 0 | N/P | N/P | N/P
Other Work | 2 | 1 | 0 | N/P | N/P | N/P
Rolling Off
3
CNB
Children’s Health Center
Santa Clara County OE
78%
Utilized
This week
Based on forecast
Migration automation
  Full end to end automation
  Additional post-migration operations setup automation
  Getting the team to actually use the automation!
WVD deployment process documentation, scripts, automation, training
2
Resources Scheduled
To Migrate
This week so far
-
Landing Zone
-
0

## Slide 2
Cloud Service Center Metrics
CMC Utilization %
Forecast
Work Items by Client
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
CNB | 0 | 4 | 0 | 0
STTAS | 2 | 0 | 0 | 0
Childrens | 1 | 1 | 0 | 0
SCCOE | 1 | 0 | 0 | 0
BassPro | 0 | 0 | 2 | 0
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned) | Two Weeks Out | Three Weeks Out
Percent Utilized | 1.3587 | 1.18 | 0.78 | 1.03 | 1.73 | 1.68
Total Migrated Resources
Chart: 
| 2 Weeks Ago | Last Week | This Week (Planned) | Next Week (Planned)
VMs | 2 | 4 | 2 | 0
DB | 0 | 0 | 0 | 0
CMC Utilization %
Actual Billed
Chart: 
| 2 Weeks Ago | Last Week
Percent Utilized | 0.96196 | 0.53261