## Sheet1
Migration Group CheckList
Migration Group:
Client:
Technical Onbaording Manager:
Prerequisite: | Completed? | Notes
Did we get the 10VU, server list, application list from client? |  | Ask for Location
Did we get VCenter Access credentials? |  | Where are the Credentials
Landing Zone Information (naming conventions, network architecture, etc) |  | Ask for location
List of applications that the client wants prioritized (Preferably in list of easy-hard to move) |  | Ask for location
Client - AZDO board is built for migration tracking. |  | if yes ask for acccess
Capacity planning done? (How many servers we can migrate at a time) |  | Ask for the location of the documentation capacity planning
ASR componants deployed into client environment (Configuration server, vault, regions identified, etc)? |  | yes or no
Work with Client on proposed Migration schedule developed from client discovery meetings. Outcome (Pilot group(s), first few applications to move and their owners)
Week 1 - Discovery Planning - Review Apps and Planning | Completed? | Notes
App Owner contacts
Send out a Welcome Kit/Workload Discovery to App owner
Review Welcome Kit
Breakdown of Application migration plan. (Intro to the migration PPT deck)
Pre-schedule Arch Review with Cloud Arch. Outcome of this meeting: Checklist, landing information, what needs to be built for the CMC to land the app and who is building it.
Review of Backlog.
Uploading the App/Server list to CMC Migration Board AZDO (Azure DevOps)
Update Card in Client AZDO board
Week 2 - Replication - Azure Site Recovery (ASR) | Completed? | Notes
CMC started replication
CMC does failover testing
Make sure CMC Update Card in ADO (Azure DevOps)
Go / No Go call (With checklist from discovery process week 1)
Week 3 - Non-Prod (Dev,Test,Stage) - Failover | Completed? | Notes
Make sure CMC engineer Update ADO Board
Set up a Migration Bridge for CMC and APP owners (In checklist)
Week 3 - Prod | Completed? | Notes
Ensure Migration Bridge for CMC and APP owners is created (In checklist)
Make sure CMC Update Card in ADO