Migration Planning and Execution – Week by Week

Week 1: 
Discovery Planning - Review Apps and Planning
The goal for Week 1 is to schedule and review Welcome Kit/Workload Discovery with client gathering information, dependencies, timeline and build a plan for migrating the workload or workload group.

Week 2: 
Replication - Azure Site Recovery (ASR) 
ARS has started to replicate the client's current environment.

Week 3: 
Non-Prod - Testing 
CMC will insulate the replicated VM environment in Azure for client testing.

Week 4: 
Production - Finalizing Migration
CMC will move the tested VM to production in Azure and shutdown the On Prem production of the client server. 


2 Week - Post Project Support
Post Migration 
Our client is Live with a 2-week post period with the CMC (Cloud Migration Center) engineering team.

Below is an example of the client migration Cadence week by week.

This will be a rinse and repeat process for each group.

| WEEK 1 PLANNING | TASK Discovery Planning: Migration Group 1 (Pilot migration) - Discovery Planning (Welcome Kit) - Send out Welcome Kit after call with Client. - Link to Welcome Kit/ WorkLoad Discovery - Preschedule ASR (Azure Site Recovery) review with client and Coud Architect. - Review Migration Process and APPs from the returned Welcome Kit with client again - Review Scope of Work with client for Migration Group 1 Link to migration Process PowerPoint - Ask Questions about current app migration to Azure. - Do they use Citrix to access any apps? - Do they use any tagging lists? - Any current issues with current applications such as Latency, interruption issues, consistent errors etc. - Does it share databases across multiple applications? - Does the app need 3rd party Assistance? - If so, ask the client for 3rd Party contact information. - Do the vendors own the database? - Ask the client to supply information about the 3rd party team or whoever externally has them involved in the migration of the software. This will allow us to pre-plan migrations for the next 3 - 4 weeks starting with a Pilot Migration - Migration Group 1 |
| --- | --- |
| WEEK 2 PLANNING | TASK Migration Group 2 - Discovery Planning (Welcome Kit) Migration Group 1 (Pilot migration) - Replication Migration Group 1 - Arch Review Meeting with Client by TOM, Cloud Architect and APP owner - CMC Engineer start the replication on client server/apps. Migration Group 2 Start Discovery Planning - Send out a Welcome Kit / Workload Discovery - Preschedule Arch Review Meeting with Client including TOM, Cloud Architect and APP owner Review Migration Process and APPs from the return Welcome Kit with client again - Review Scope of Work with client for Migration Group 2 Link to migration Process PowerPoint (if needed) Ask Questions about current app migration to Azure. - Do they use Citrix to access any apps? - Do they use any tagging lists? - Any current issues with current applications such as Latency, stoppage issues, consistent errors etc. - Does it share databases across multiple applications? - Does the app need 3rd party Assistance? - If so, ask the client for 3rd Party contact information. - Do the vendors own the database? - Ask the client to supply information about the 3rd party team or whoever externally has them involved in the migration of the software. |
| WEEK 3 PLANNING | TASK Migration Group 3 - Discovery Planning (Welcome Kit) Migration Group 2 - CMC starts Replication. Migration Group 1 (Pilot migration) - Migration Migration Group 3 - Start Discovery Planning - Send out a Welcome Kit / Workload Discovery - Preschedule Arch Review Meeting with Client (Schedule a week out.) - Including TOM, Cloud Architect and APP owners - Review Migration Process and APPs from the return Welcome Kit with client again - Review Scope of Work with client for Migration Group 3 Link to migration Process PowerPoint (if needed) - Ask Questions about current app migration to Azure. - Do they use Citrix to access any apps? - Do they use any tagging lists? - Any current issues with current applications such as Latency, downtime issues, consistent errors etc. - Does it share databases across multiple applications? - Does the app need 3rd party Assistance? - If so, ask the client for 3rd Party contact information. - Do the vendors own the database? - Ask the client to supply information about the 3rd party team or whoever externally has them involved in the migration of the software. Migration Group 2 - Arch Review Meeting with Client by TOM, Cloud Architect and APP owner - CMC Engineer start the replication on client server/apps. Migration Group 1 - Start NON-Prod Migration This will be being with by CMC Engineer. |
| WEEK 4 PLANNING | TASK Migration Group 4 - CMC starts Replication. Migration Group 3 - Non-Production (For DEV, Testing, UAT. Before the official migration) Migration Group 2 - Production (Migration to Azure) Migration Group 1 - Postproduction (2 Weeks and Decom) Migration Group 4 Start Discovery Planning - Send out a Welcome Kit / Workload Discovery - Preschedule Arch Review Meeting with Client (Schedule a week out.) - Including TOM, Cloud Architect and APP owner - Review Migration Process and APPs from the return Welcome Kit with client again - Review Scope of Work with client for Migration Group 4 Link to migration Process PowerPoint (if required) - Ask Questions about current app migration to Azure. - Do they use Citrix to access any apps? - Do they use any tagging lists? - Any current issues with current applications such as Latency, stoppage issues, consistent errors etc. - Does it share databases across multiple applications? - Does the app need 3rd party Assistance? - If so, ask the client for 3rd Party contact information. - Do the vendors own the database? - Ask the client to supply information about the 3rd party team or whoever externally has them involved in the migration of the software. Migration Group 3 - Arch Review Meeting with Client by TOM, Cloud Architect and APP owner - CMC Engineer start the replication on client server/apps. Migration Group 2 - Start NON-Prod Migration. This will be handled by a CMC Engineer. Migration Group 1 - Migration to Azure |
| WEEK 5 | TASK Migration Group 5 - Discovery Planning (Welcome Kit) Migration Group 4 - CMC starts Replication. Migration Group 3 - Non-Production (For DEV, Testing, UAT. Before the official migration) Migration Group 2 - Production (Migration to Azure) Migration Group 1 - Postproduction (2 Weeks with CMC and Transition to Managed Services) Migration Group 5 Start Discovery Planning - Send out a Welcome Kit / Workload Discovery - Preschedule Arch Review Meeting with Client (Schedule a week out.) - Include TOM, Arch and APP owner - Review Migration Process and APPs from the return Welcome Kit with client again - Review Scope of Work with client for Migration Group 4 Link to migration Process PowerPoint (if required) - Ask Questions about current app migration to Azure. - Do they use Citrix to access any apps? - Do they use any tagging lists? - Any current issues with current applications such as Latency, downtime issues, consistent errors etc. - Does it share databases across multiple applications? - Does the app need 3rd party Assistance? - If so, ask the client for 3rd Party information. - Do the vendors own the database? - Ask the client to supply information about the 3rd party team or whoever externally has them involved in the migration of the software. - Migration Group 4 - Arch Review Meeting with Client by TOM, Cloud Architect and app owner - CMC Engineer start the replication on client server/apps. - Migration Group 3 - Start NON-Prod Migration. This will be handled by a CMC Engineer. - Migration Group 2 - Production - Migration to Azure - Migration Group 1 - Post Migration - 2 Week Post Support (CMC) - Transition to Managed Services |

When communicating with the client.

Remember to ALWAYS document and recap all conversations with client!