Technical Onboarding Manager (TOM)

Client Onboarding Process Step by Step

Step 1 - Project ANNOUCEMENT (Pre-Staffing)
 Once Order has been approved and Won. Notification will be sent out to Lead Engineer showing who will be part of the STAFFING for the new project.

Step 2 - DD will schedule the Internal Kick Off Meeting

DM (Delivery Manager) or DD (Delivery Director) will schedule an Internal Kickoff with the Internal Team Members that will be involved in this project.

The call will include the following people:

- Delivery Director/Delivery Manager

  - Will introduce the client to us.

- Architect (Tech Lead)

  - Assesses the building of the client incoming server on Azure and Arch will hand it over to CMC (Cloud Migration Center).

  - Arch will schedule the migration data.

- CMC (Cloud Migration Center) Lead

  - CMC will do the work of the migration and will work closely with Architect.

- Technical Onboarding Manager (TOM) - 
(This will depend on the SOW (Statement of Work)

  - Ask the DD about server/app information.

  - Do they have a 10 VU?

  - Do we have Server list?

  - Prep and Send out Welcome Kit using info from SOW internal Meeting.

*Possible Client Partner and Solution Architect may join Internal Meeting.

In the Kickoff internal Meeting, DD will review the following:

- Client High Level

- Migration Expectations

- Migration Hours

- DD or DM (Delivery Manager) will schedule the external Kick Off.

STEP 3 - External Kick Off Call - 30 Min Call introduction

- DD or DM/Architect will lead the conversation.

- CMC will introduce themselves.

  - Possible answer questions about the process

- Next Steps after external calls

  - Request VCenter access/Datacenter access (CMC Lead or TOM)

    - TOM will need to ask Lead which engineer will be assigned.

    - Once we receive access, CMC will build the ASR (Azure Site Recovery).
	Usually at least 1 week prior to the Pilot Migration.

*Server OS (Operating System) must be Windows 2008 and above to migrate to Azure.

STEP 4 – Schedule Discovery Call with Client

- Determine Server and Application Dependency

  - Preliminary Server List from client

  - Request Low risk apps for Pilot Migration.

- Loose prioritization of app migration plan

- After confirming with the client, send out the welcome kit for the first Pilot Migration Group.

Step 5 - Migration Planning and Execution - Technical Onboarding Manager

Ideally Migration is done in 4-week sprints starting with the easiest first. Apps will need to be divided into groups from minimal impact to high impact. The first migration group should always have the lowest impact on the client and their users.